FY06 EUSE/ULUG Work Plan Guidance for Study Units
EFFECTS OF URBANIZATION ON STREAM ECOSYSTEMS (EUSE)

This document provides FY06 guidance for the Topical Team assessing the “Effects of Urbanization on Streams Ecosystems” (EUSE/ULUG). The Group 1 or ‘01 Study Units include the ACFB, ALBE, SPLT, TRIN, WILL, and WMIC.  The Group 2 or ‘04 Study Units include the PUGT and SACR. Information in this document is based upon the December 2003 draft work plan (http://cointernal.cr.usgs.gov/nawqa/urban/index.html) and updated reports plan developed at the EUSE national meeting in Denver April 12-15, 2005.
For purposes of FY06 budgets, all study units should determine both salary and non-salary estimates, including travel and attendance to meeting and workshops. See FY06_EUSE_guidance_timeline.xls for developing the work plan. This document gives the general timeline for tasks that the team developed at the April 2005 EUSE meeting in Denver. 
Group 1 Study Units (ACFB, ALBE, SPLT, TRIN, WILL, WMIC)
Study Unit Reports:

· ACFB, ALBE, SPLT Study Unit Reports to be published by January 2006.
· TRIN, WILL, WMIC a first draft of Study Unit Reports should be completed in the March to June timeframe.
· See FY06_EUSE_guidance_timeline.xls for time line and task associated with Study Unit Reports.
National Reports:

· Data analyses and report writing for national reports identified in the reports plan will begin in FY06. See FY06_EUSE_guidance_timeline.xls for time line and task associated with National Reports.
Data Archival: 
· It is in the best interest of the Study Unit and the National team to keep up with data and information archival while people are still on the NAWQA project. To that end, Jana Stewart has compiled an Archival worksheet for the team (FY06_EUSE_archival_checklist.xls). This worksheet needs to be completed each year to help keep track of datasets and information.

· ALL study units need to submit a plan for data archival in their work plan in August.
· Final Archival worksheet for study unit will be due in January 2006.

Budgets for Group 1 Study Units:  

· All target budgets for EUSE work in FY06 include:

· Personnel time for data archival, Study Unit Reports, and National Reports as determined at the EUSE National Meeting and updated by Report Leads are given in the workbook FY06_EUSE_Personnel_SU_and_Natl_Reports_Summary.xls.
· Travel funds of $5000, report printing costs of $4,000 and report processing funds of $2,000.
Group 2: ‘04 Study Units (PUGT, SACR):

· Plan and continue to update EUSE design and collaborations for both study units.
· Plan to attend a national meeting and/or regional meetings in FY06.
· Update any training needed for field sampling (e.g., fish certification)

· See FY06_EUSE_guidance_timeline.xls for time line and task associated with study unit activities.
SACR

· Process NLCD 2000 including impervious surface and land cover for SACR
· Determine appropriate study area

· Purchase imagery for the study area

· Purchase software to process images

· Attend training on processing imagery at EDC or other alternative training

· Process data to complete the land cover and impervious surface products

· Estimate this will require about 0.42 % of GIS person’s time

· Participate in field reconnaissance with PUGT as training activity

PUGT
· Site selection process:

· Process data to complete the BASINCHAR spreadsheet for Candidate basins (Consult with Jana Stewart and James Falcone)
· Compute urban intensity index (UII) for candidate basins

· Look at environmental setting information to determine where approximately 30 sites representing the range of urban intensity can be located.
· Conduct reconnaissance of sites to assess physical access and local stream conditions such as, land use, point sources, riparian condition, and instream habitat characteristics.
· Select 30 sites and rerun the UII index based on specific site location
· Transducer installation:

· Get permissions for sampling and installing transducers

· Install transducers approximately one year prior to the last data collection and check to determine if working properly.
Budgets for Group 1 and Group 2 Study Units:

See FY 2006 Work Plan budget on the NAWQA internal page for individual study unit budget targets.
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