FY07 Work Plan Guidance

Ground-Water Status & Trends Flow-System Studies 

April 7, 2006
Ground-Water Status & Trends (GW S&T) is proposing to start 5 FSSs (Flow-System Studies) in FY07.  These 5 FSSs are nested within 5 Group 2 Study Unit Land-Use Studies that are part of the national trends network.  A primary purpose of these FSSs is to aid interpretation of trends in the nested land-use studies.  

The five FSSs are nested in:

santluscr1   (Ag)

linjlusrc1    (Urban Glassboro)

pugtluscr1  (Ag)

umislusrc1 (Urban Minneapolis)

lerilusrc1    (Urban Detroit)

These 5 FSSs were among the 8 highest-ranked FSSs proposed by NIT in 2001.  In 2005, an FSS 2005 Planning Team reviewed the NIT plan for FSSs, determined that, at most, GW S&T could afford to do only 5 FSSs in Group 2 study units and stay within the budget planned for FSSs by NIT, and recommended the 5 FSSs listed above.   An internal document summarizing the Planning Team's review and recommendations to NLT is located at   http://water.usgs.gov/nawqa-only/gwst/fss_plan.html.

Jim Tesoriero (FSS Lead), Larry Puckett (Nutrient Nat Syn), David Saad (WMIC) and Wayne Lapham (GW S&T Coordinator) held a conference call on April 11, 2006 with the 5 study units, the ARHN’s and selected Principal Aquifer Lead Scientists to begin discussion and planning of these FSSs.  Powerpoint presentations of material covered during this call are located at http://water.usgs.gov/nawqa-only/gwst/fss_plan.html.
Jim Tesoriero needs to include his 1/2 time salary in the WILL study-unit budget for coordinating the Group 2 study-unit flow-system study planning, design and implementation and for his participation on the GW Trends core team. 
During spring/summer, 2006, the 5 study units that will start FSSs in FY07 (SANT, LINJ, PUGT, UMIS and LERI) have worked with the FSS Lead and others to develop estimates of the cost of FSS design and well installation, and need to include those costs in their study-unit budgets.
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