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The purpose of this guidance is to summarize work elements for FY11 for NAWQA GW S&T (Ground Water Status and Trends) Data Analysis & Reports.  The specific data analysis and reports activities are listed below.  In parentheses are the leads for developing the FY11 work plans and budgets for these efforts, in coordination with the RNPOs (Regional NAWQA Program Officers) and Wayne Lapham.

1. PA (Principal Aquifer) Lead Scientist activities (PA LSs: Principal Aquifer Lead Scientists).

2. PA analysis & reporting, including PA foundational reports and PA Circulars (PA LSs and report leads).
3. PA Circular planning: (Tracy Hancock, Wayne Lapham).

4. End-of-2009 frozen QW occurrence data set for national comparative graphics for Appendix 3 of the PA Circulars  (Leslie Desimone, Terri Arnold, Sharon Qi).

5. Internal and public PA web pages on GW QW occurrence, distribution and trends (Mike Rupert, Terri Arnold).  
6. GW Trends analysis & reporting, including foundational reports (Bruce Lindsey with the GW Trends team).

7. PA Summary Circular (Leslie Desimone, Pete McMahon, Michael Rosen).
8. GIS of Principal Aquifers; Land-use land-cover characterization around wells; NAWQA GW S&T report data archive reviews (Terri Arnold, Sharon Qi). 
Following are the responsibilities of each Lead listed above in helping to develop FY11 work plans and budgets for GW S&T analysis and report activities.

General note:  Budgets for GW S&T analysis and reports activities are submitted using the budget template (FY05-FY13_ReportBudgets_template.zip) on the USGS web page below under Budgets (login using your Lotus internet username and password):
 https://gsvaresa07.er.usgs.gov/QuickPlace/gwst_pa/Main.nsf?OpenDatabase.
Please use this template for estimating the cost of GW S&T analysis and reports activities for FY11 and beyond, including the log update file, action items, report time-task lines and budgets.   Please check out and revise, as needed, an existing budget or download, fill in and save the blank template for a new report activity.  Once completed, please check the budget file back in to the Quickr site.
(1) PA LS activities:  PA LSs activities generally include:

(a) Tracking, reviewing progress, and technical reviews of on-going GW S&T reports in their PA(s);

(b) Working with Wayne Lapham, the RNPOs (Regional NAWQA Program Officers) and Study-Unit Chiefs during the spring and early summer of 2010 to finalize, as needed, FY2011 work plans for GW S&T analysis and reporting in the PA(s);


(c) Continuing work on the PA Circulars.  A draft of each Circular needs to be completed and ready for review by the end of the 3rd quarter of FY11:  Specific FY11 tasks include writing the following chapters of the Circular: (1) Introduction; (2) Water-Quality Overview (Executive Summary); (3) Summary of Major Findings and Implications; (4) Key Stories; (5) Challenges & Opportunities; and (6) References.  
 (d) Participating in discussions of possible NAWQA/Cooperative or other discipline program work;

(e) Communicating our work and findings; and

(f)  Helping to track progress on NAWQA FY11 sampling and related field activities in the PA(s), if requested.

(2) PA Analysis and Reporting:  

The current (April 2010), proposed plans and budgets for GW S&T analysis and reports activities are on the USGS web page under Reports Plans and Budgets, respectively: 

 https://gsvaresa07.er.usgs.gov/QuickPlace/gwst_pa/Main.nsf?OpenDatabase.

PA Lead Scientists, if necessary, need to update their report plans for FY11 and beyond, and ensure that the FY11 cost estimates are included in the respective Study-Unit budgets (PA LSs and teams).  Please remember to include any report costs (except for the PA Circulars) needed in FY11 for EPN and GPO. 

(3) PA Circular Planning: Tracy Hancock and Wayne Lapham are responsible for working with the PA LSs to plan FY11 work on the PA Circulars including conference calls, meetings and writing Circular chapter drafts.  Specific Circular chapters that need to be written in FY11 are the: (1) Introduction; (2) Water-Quality Overview (Executive Summary); (3) Summary of Major Findings and Implications; (4) Key Stories; (5) Challenges & Opportunities; and (6) References.
(4) End-of-2009 frozen QW occurrence data set for national comparative graphics for Appendix 3 of the PA Circulars:
Leslie Desimone, Terri Arnold and Sharon Qi are responsible for continuing this effort in FY11.  This effort needs to be completed as early as possible in FY11 (if not in FY10) for use by the PA Circular authors.

(5a) Internal and public web pages on ground-water trends:

Mike Rupert, GW Trends team, will continue to develop the ground-water trends mapper as part of reporting on ground-water trends at the national, regional and local (by well) scales.

 (5b) Internal and public web pages on the status of ground-water quality (occurrence and distribution):

Terri Arnold will continue development of PA internal and external web pages on the status of water-quality conditions at the national, regional and local (by well) scales.    Work on the proposed public web site that summarizes water-quality conditions at various scales needs to be closely coordinated with the work that Mike Rupert is doing in (5a) on GW Trends.
(6) Ground-Water Trends Analysis and Reporting:  
Bruce Lindsey, Lead, GW Trends team is responsible for developing an FY11 work plan and budget for GW Trends activities in FY11-12 to include plans for analysis & reporting on Simulation & Forecasting studies, Understanding Factors studies, and national, regional and local trends in ground-water quality.
(7) PA Summary Circular

Leslie Desimone, Lead, PA Summary Circular team is responsible for developing and implementing a plan for a PA Summary Circular to be published simultaneously with publication of the PA Circulars and Ground-Water Trends Circular by end of 2012.
(8) GIS of Principal Aquifers, Land-use land-cover characterization around wells, NAWQA GW S&T report data archive reviews and other PA-wide activities
Terri Arnold and Sharon Qi need to include funding in the UIRB / LIRB study unit and CO budget (respectively) to support continued work on GIS of Principal Aquifers, land-use land-cover characterization around wells, NAWQA GW S&T report data archive reviews and other PA-wide support activities, as agreed upon by Terri, Sharon and the GW S&T Coordinator.
FY11.GW.DataAnal&Repts.20100420
April 21, 2010
1

