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1. ACTION: By January 15, 2012 Enter into BioData all field data for macroinvertebrate, algae, fish, and habitat samples collected during CY 2011. DO NOT ENTER DATA INTO BIO-TDB.  Entering data into BioData promptly when returning from the field will make it easier to resolve problems before they impact laboratory analyses and data users.  Data review of all CY 2011 data in BioData is also to be completed by this date.  Data review procedures for BioData are currently in development, and further guidance will be provided during FY11.  

Study units should continue to review legacy data in Bio-TDB, following procedures described in the FY11 Work Plan Guidance, and any other data review instructions provided during FY11.  For questions about data review requirements for NAWQA data, contact Marty Gurtz (megurtz@usgs.gov).  To obtain assistance, guidance, or clarification of BioData review procedures, contact Mitch Harris (maharris@usgs.gov). 

2. ACTION: By April 15, 2012 repeat the data review steps in BioData and confirm that all problems have been resolved for samples collected during CY 2011.
Periodic review of the issues raised by the data checking subsystem is necessary to ensure that the NAWQA databases are well-maintained.

3. REMINDER: Fish QA plans are to be updated annually.
Fish Quality Assurance QA Plans are to be updated annually with information about collecting permits and noting any changes in: (1) ichthyologist, (2) locations of vouchered specimens, (3) status of listed species, (4) status of electrofishing certification and CPR training for personnel involved in sampling, or (5) other changes that may significantly affect fish collection. Updates are to be sent electronically to Mike Meador (mrmeador@usgs.gov). Information regarding the creation and maintenance of the QA plans can be found in Walsh and Meador (1998) located at http://water.usgs.gov/nawqa/protocols/WRI98-4239/index.html. An entry should be made in the SWPLAN spreadsheet each year to indicate that the plan has been submitted for that year’s sampling effort, for any site where fish collections are scheduled (see “Workplan Guidance for NAWQA Surface-Water Status and Trends Sampling and Reports”).

The table below indicates the most recent version of a Fish QA Plan that a study unit has filed with the ENS team (dates in bold reflect an update since the FY11 annual work plan guidance). Study units in RED are active study units that have not submitted an update for the most recent year of fish collections. 
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	Region
	SUID
	DATE

	CR
	ACAD
	6/18/2004

	CR
	CNBR
	7/29/2009

	CR
	EIWA
	2/14/2011

	CR
	OZRK
	5/5/2008

	CR
	RIOG
	7/14/2010

	CR
	SCTX
	8/1/2006

	CR
	SPLT
	8/18/2006

	CR
	TRIN
	8/1/2006

	CR
	UMIS
	7/17/2008

	CR
	YELL
	7/7/2008

	NR
	CONN
	6/19/2008

	NR
	DELR
	6/12/2009

	NR
	HDSN
	7/23/2009

	NR
	LERI
	7/21/2009

	NR
	LINJ
	7/18/2003

	NR
	PODL
	7/22/2009

	NR
	UIRB
	6/15/2005

	NR
	WHMI
	2/7/2011

	NR
	WMIC
	6/23/2010

	SE
	ACFB
	9/10/2010

	SE
	ALBE
	3/8/2011

	SE
	MOBL
	5/12/2005

	SE
	SANT
	12/23/2010

	SE
	TENN
	7/5/2005

	WR
	CAZB
	8/13/2007

	WR
	CCYK
	10/4/2005

	WR
	GRSL
	9/1/2005

	WR
	PUGT
	10/4/2005

	WR
	SACR
	8/12/2005

	WR
	SANJ
	8/12/2005

	WR
	SOCA
	4/29/2009

	WR
	USNK
	7/12/2010

	WR
	WILL
	8/26/2007





2
Page 2 of 2
