# FY12 Work Plan Guidance from Ecological National Synthesis Team

## 1. ACTION: By January 15, 2012 Enter into BioData all field data for macroinvertebrate, algae, fish, and habitat samples collected during CY 2011. DO NOT ENTER DATA INTO BIO-TDB.  Entering data into BioData promptly when returning from the field will make it easier to resolve problems before they impact laboratory analyses and data users.  Data review of all CY 2011 data in BioData is also to be completed by this date.  Data review procedures for BioData are currently in development, and further guidance will be provided during FY11.

Study units should continue to review legacy data in Bio-TDB, following procedures described in the FY11 Work Plan Guidance, and any other data review instructions provided during FY11.  For questions about data review requirements for NAWQA data, contact Marty Gurtz (megurtz@usgs.gov).  To obtain assistance, guidance, or clarification of BioData review procedures, contact Mitch Harris (maharris@usgs.gov).

2. ACTION: By April 15, 2012 repeat the data review steps in BioData and confirm that all problems have been resolved for samples collected during CY 2011.

Periodic review of the issues raised by the data checking subsystem is necessary to ensure that the NAWQA databases are well-maintained.

3. REMINDER: Fish QA plans are to be updated annually.

## Fish Quality Assurance QA Plans are to be updated annually with information about collecting permits and noting any changes in: (1) ichthyologist, (2) locations of vouchered specimens, (3) status of listed species, (4) status of electrofishing certification and CPR training for personnel involved in sampling, or (5) other changes that may significantly affect fish collection. Updates are to be sent electronically to Mike Meador (mrmeador@usgs.gov). Information regarding the creation and maintenance of the QA plans can be found in Walsh and Meador (1998) located at http://water.usgs.gov/nawqa/protocols/WRI98-4239/index.html. An entry should be made in the SWPLAN spreadsheet each year to indicate that the plan has been submitted for that year’s sampling effort, for any site where fish collections are scheduled (see “Workplan Guidance for NAWQA Surface-Water Status and Trends Sampling and Reports”).

The table below indicates the most recent version of a Fish QA Plan that a study unit has filed with the ENS team (dates in bold reflect an update since the FY11 annual work plan guidance). Study units in RED are active study units that have not submitted an update for the most recent year of fish collections.

| Region | SUID | DATE |
| --- | --- | --- |
| CR | ACAD | 6/18/2004 |
| CR | CNBR | 7/29/2009 |
| CR | EIWA | 2/14/2011 |
| CR | OZRK | 5/5/2008 |
| CR | RIOG | 7/14/2010 |
| CR | SCTX | 8/1/2006 |
| CR | SPLT | 8/18/2006 |
| CR | TRIN | 8/1/2006 |
| CR | UMIS | 7/17/2008 |
| CR | YELL | 7/7/2008 |
| NR | CONN | 6/19/2008 |
| NR | DELR | 6/12/2009 |
| NR | HDSN | 7/23/2009 |
| NR | LERI | 7/21/2009 |
| NR | LINJ | 7/18/2003 |
| NR | PODL | 7/22/2009 |
| NR | UIRB | 6/15/2005 |
| NR | WHMI | 2/7/2011 |
| NR | WMIC | 6/23/2010 |
| SE | ACFB | 9/10/2010 |
| SE | ALBE | 3/8/2011 |
| SE | MOBL | 5/12/2005 |
| SE | SANT | 12/23/2010 |
| SE | TENN | 7/5/2005 |
| WR | CAZB | 8/13/2007 |
| WR | CCYK | 10/4/2005 |
| WR | GRSL | 9/1/2005 |
| WR | PUGT | 10/4/2005 |
| WR | SACR | 8/12/2005 |
| WR | SANJ | 8/12/2005 |
| WR | SOCA | 4/29/2009 |
| WR | USNK | 7/12/2010 |
| WR | WILL | 8/26/2007 |