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The purpose of this guidance is to summarize FY13 reporting activities for NAWQA Groundwater Assessments.  In parentheses are the leads for developing the FY13 work plans and budgets for these activities, in coordination with the RNPOs (Regional NAWQA Program Officers), Wayne Lapham, Ken Belitz, and Terri Arnold. Barbara Mahler and Wayne Lapham are responsible for planning, overseeing and coordinating work on all of the PA Circulars.  They also will coordinate work on the Circulars with the 3 Publication Service Centers, and will work with the PA LSs and NLT to develop communication plans for release of the Circulars.

1. PA LS (Principal Aquifer Lead Scientist) activities and PA Circulars (PA LSs).
2. PA Summary Circular (Leslie Desimone).
3. PA Circular planning and coordination (Wayne Lapham and Barbara Mahler).
4. Internal and public PA & PA Circular supporting web pages (Sharon Qi, PA LSs).
5. GIS of Principal Aquifers and NAWQA GW S&T report data archive reviews (Sharon Qi). 

The current (July 2012) proposed plans for FY13 GW S&T reports activities include the following: 

	NAWQA reports portfolio ID
	Report topic

	60
	METX-Circular

	59
	DENV-Circular

	61
	FLOR-Circular

	64
	GLAC-Circular

	62
	NACP-Circular

	PA-wide Rept 7
	PA Summary Circular

	63
	PIED-Circular

	58
	SWPA-Circular

	57
	WVOL- Circular


 

PA Lead Scientists need to update their cost estimates for completing their PA circular, and implementing the communication plan in FY13. Ensure that the FY13 cost estimates are included in the respective FY13 Water Science Center budgets, taking into consideration the funds you may have already received in FY12 to carry over to FY13.

For the PA Circulars, please remember that SPN and GPO costs are already set aside at Headquarters in a Working Capital Fund, so these costs should not be included in Water Science Center budgets.
 
Following are the responsibilities of each Lead listed above in helping to develop FY13 work plans and budgets for GW S&T report activities. Please contact Wayne Lapham if you have questions about work on the circulars.


(1) PA LS activities and the PA Circulars  

PA LS report activities for FY13 are focused on completing the PA Circulars.

(a) Finishing and publishing the PA Circulars.  The circulars are to be published in FY13. 
-  Working with SPN on graphics, photos, revising the Circular based on SPN's editorial review, addressing comments from the Bureau Approving Official, and preparing final report for printing and distribution.

-  Building Circular supporting web page(s) to include additional information that could not be included in the Circular, but that the PA LS wants to make sure is available to support it: for example - data sets used; additional summary maps and tables; information to support graphics; occurrence boxplots; web links to important web sites; etc.
- Developing and implementing a Communications Plan for roll out of their Circular in coordination with NLT.  

(b) Working with Wayne Lapham, the RNPOs (Regional NAWQA Program Officers) and NAWQA designated contacts in Water Science Centers to finalize, as needed, FY13 work plans and budgets related to completing the circulars;


(2) PA Summary Circular

Leslie Desimone, Lead for the PA Summary Circular, is responsible for completing the PA Summary Circular to be published in 2013.

(3) Internal and public PA & PA Circular supporting web pages

Sharon Qi is responsible for working with the PA LSs to design and develop supporting internal and external web pages for each of the PA Circulars and the PA Summary Circular.  The supporting web page(s) would include additional information that could not be included in the Circular, but that the PA LS wants to make sure is available to support it.  For example, data sets used; additional summary maps and tables; information to support graphics; occurrence boxplots; web links to important web sites;

(4) GIS of Principal Aquifers, NAWQA GW S&T report data archive reviews and other PA-wide activities

Terri Arnold and Sharon Qi need to ensure the Illinois and Colorado Water Science Centers, respectively, include funding in the FY13 budgets to support continued work on GIS of Principal Aquifers (Terri and Sharon), NAWQA GW S&T report data archive reviews (Sharon), continued development and maintenance of the PA internal and public web pages (Sharon and Terri), and other PA-wide support activities (Terri and Sharon), as agreed upon by Terri, Sharon and the Groundwater Assessment and Synthesis Coordinator.



