## Sheet1
FY13 Work Plan Guidance Changes | Change Date | Person Responsible | Change
FY13.WPG.Targets.xlsx | 2012-08-02 | T. Arnold | updated lab prices for radionnuclides, contract with Eberline (NWQL) started 8/1/2012
SWPLAN | 2012-08-02 | D. Reutter | updated Eco worksheet
FY13.WPG.Targets.xlsx | 2012-08-03 | T. Arnold | updated lab holds, and distributed pending radium sample counts to network planned samples
FY13.WPG.Targets.xlsx | 2012-08-06 | T. Arnold | added funding for water levels in the NECBsus3 network, and placed a hold on funds for a new PAS in the Piedmont/Valley and Ridge aquifer.
FY13.GWST.WPG.Table1.xlsx | 2012-08-06 | T. Arnold | added NECBsus3 network in table 1 for water levels in FY13. In the cycle 3 implementation plan, necbsus3 was a postponed network. It is now added into the cycle 3 sampling schedule because some interesting MTBE trends have been identified in that area. This decision was made during a call with Ken Belitz and Bruce Lindsey on 8/2/12.
FY13.SC.BudgetTemplate.xlsx | 2012-08-09 | R. Musson | Added 4 SW QW Site columns to the SW M&SA Staffing and SW M&SA Budget worksheets.
FY13.NFSN.WPG.docx | 2012-08-16 | D. Reutter | Laboratory Information --removed statement --"NASQAN and NMN samples should still use the account numbers that have been used in previous years - account GX13DD009CE0000 for the NASQAN samples and GX13DD009U2LA00 for the NMN samples." In FY13, the NMN and NASQAN National account numbers will not be used. NMN and NASQAN NWQL samples will be charged to a NAWQA/NWQL prepaid account number. ASR forms should use the local science center account number as a reference account number along with the correct Proposal Number and Project Code, and the sample charges will automatically be charged to the NAWQA/NWQL.
FY13.SC.BudgetTemplate.xlsx | 2012-08-23 | R. Musson | Fixed SC Summary col c formulas, and SW Staffing cell F8
FY13.WPG.Targets.xlsx | 2012-08-27 | T. Arnold | Change is holds listed below Science Center targets including decreasing sampling estimates and increasing PIED PAS hold to fund a 60-well network instead of the previously planned 40-well network.
FY13.WPG.Matrix.xlsx | 2012-09-04 | T. Arnold | Removed 'WP' from MA, NJ, PA, TN, LA, NM, WY, AZ because those states do not have GW work to budget for in FY13.
FY13.WPG.Targets.xlsx | 2012-09-04 | T. Arnold | Adjusted salary estimate for Assistant Coordinator
FY13.GWST.WPG.Table1.xlsx | 2012-09-24 | T. Arnold | Updated CT, FL, and IL, and added an "update date" at the top of the worksheet.
FY13.GWST.WPG.Table1.xlsx | 2012-10-05 | T. Arnold | 1) Changed the heading of column G to be more explicit "Sampling or Waterlevels should be completed by the end of the month", and updated column G. 2) Updated the sampling month to June from October for nvbrlusrc1 after looking at past sampling dates and a discussion it with Jena Huntington. 3) Added a README_updates tab.
SWPLAN | 2012-11-29 | D. Reutter | Addition of the five new NFSN sites (AZ, KS, ND, and OK WSCs) Removal of field blanks required for the suspended sediment samples
FY13.NFSN.WPG.docx | 2012-11-29 | D. Reutter | Various updates to the sampling protocol after the review by Stan Skrobialowski.