Meeting Notes for Conference Call on November 2, 2006
Attendees: Mary Ann Thomas and Chris Hoard (LERI), Jim Stark (UMIS), Sandy Embrey (PUGT), Jeff Fischer and Zoltan Szabo (LINJ), Celeste Journey (SANT), Jim Tesoriero, Wayne Lapham, Larry Puckett, Mike Yurewicz  
Meeting notes prepared by Jim Tesoriero.
RE: Plans for FY2007

A. Site Selection, network installation, well replacements – 
1. LINJ: 

(Have not selected site yet. 

(Will contact Sandy Eberts regarding site selection.

(A well or stream as receptor is being considered.. 

( A range of contaminants are commonly found in supply wells. Radium (naturally occurring), mercury (atmospheric source) and VOCs are of particular interest.

(Drilling is planned for the summer of 2007.

(TANC wells will be sampled in 2009.

2. LERI:

(Began looking over possible urban land use study sites using digital well log search and other office-based methods.

(Two sites of interest have been found.

(Plan to visit 3 or 4 sites during the winter.

(Drilling is planned for June 2007.

(Some areas are sub-oxic at the surface. This issue was discussed and it was decided that this condition does not preclude selection. Selection should be based on the whether the condition is representative. An oxic site at the water table that becomes sub-oxic with depth is more common in the area and is the geochemical setting that is preferable.

(Nitrate, chloride and arsenic are contaminants of interest in this study area.

3. SANT:
(Present network of multiports is in good shape with only a few (3?) ports that are not producing.

(A deep well and any replacement wells will be installed in June 2007 using the Giddings trailer mounted drill rig operated by Eric Sadorf (NC WSC). 

(Plan to sample 6 or 7 locations, with 3 depths per location.

(Sediment organic carbon (SOC) data is available and will be sent to Jim Tesoriero by Larry Puckett (done on 11/2/06).

(Jim will let Celeste know whether or not additional SOC sampling is needed.

4. UMIS:

(Status of network?? (my notes are not clear on this)

(Drilling planned for May or June 2007 with one deep well and any replacement wells installed at that time.

(SOC data has been collected. No additional SOC sampling is required at this site.

5. PUGT:

(All but 3 wells from the existing network were located and appear to be suitable for sampling.

(Replacement wells for the 3 lost wells are available so drilling may not be required.

(Drilling, if needed, will be conducted in Summer 2007 using the drill rig operated by the Oregon WSC. 

B. Review of existing data and proposed analyte schedule.

(Each study unit is to retrieve the most appropriate data for their study area. For existing FSS this will likely be the cycle 1 sampling, for the new studies LUS results and/or other studies may be selected.
( Send the data set, preferably in excel form, to me and I will distribute to others. At a minimum, include major ions, nutrients, field parameters, age dating, well depth, depth to water and the network the data are from. Include any other analytes you are interested in. 
(Within a couple of weeks of receiving the data I will schedule a call with each study unit so we can prioritize analytes.  Send these data sets to me by Feb. 1, 2007.
