SW Status & Trends Regional Synthesis Meetings

Scope

Area:  Major River Basins (MRBs), based on combined Water-Resource Regions

Disciplines:  SW hydrology, chemistry and biology

Data coverage:

USGS data at NAWQA fixed sites during Cycle I and II time period (1992 – present)

Selected NAWQA synoptic and BS&T data
(Might consider other “easily” accessible data, such as USGS at other sites or at fixed

    sites prior to 1992, and outside data IF they are similar analyses and of known quality

    and would fill gaps in the NAWQA coverage.)

Regional-Synthesis reports and Inter-Regional issues.

Parameters influencing the Regional Synthesis reports plan:

Budget – about $4M in FY04 and $5m in FY05 for SW S&T data interpretation and
                           reporting by Study Unit staff, to be divided among all MRBs

Timing – Reports must be completed by the end of FY05

Staffing – Personnel availability

Goals

1. Establish an organization for status and trends data interpretation and reporting on a regional scale.

2. Identify and prioritize specific objectives for data interpretation and reporting associated with status and trends in Cycle II.

3. Identify and prioritize issues that are important with some, but not all, study units in the region and that might be important in study units outside the region.

4. Develop a draft plan for regional data interpretation and reports for FY 04-05.

5. Determine tasks necessary for completing regional reports and identify individuals in study units who will work on these tasks.

