DRAFT PROJECT PROPOSAL

Proposal Title	Estimation of Low-low Statistics for ungaged sites on New Jersey Streams

Principal Authors	Steven Nieswand, Robert D. Schopp, Kara Watson, Ward Hickman, U.S. Geological Survey, New Jersey Water Science Center

## Problem

The demand for water for domestic use, agriculture, and recreation has increased in many areas as the population of New Jersey has grown from about 5 million people in 1950 to over 8 million people in 2000. The population increase and associated spread of development has increased the number of areas that stress the water resources of the State which can have detrimental impacts on the in stream aquatic ecology and downstream users. The ecological effects of these demands are an unintended consequence of growth, often going unnoticed until aquatic resources may be stressed beyond recovery.

To protect existing water supplies, to plan for future water supplies, and to protect and enhance the aquatic ecology, the NJDEP and USGS, through cooperative agreements, have been developing tools and strategies that can assist in allocating the water resources of the state among competing needs. One such tool is the New Jersey Hydroecological Assessment Tool (NJHAT) that can calculate 171 flow statistics at any stream site with a long term-daily streamflow record; statistics include both low- and high-flow hydrologic indices. The NJDEP has been developing streamflow requirements for water diversions that to a large extent are related to several low flow statistics. The issue is to develop flow statistics at ungaged stream sites.

A recent study by the New Jersey USGS Science Center for the New Jersey Highlands Council used streamflow records from continuous long term stream gages and partial record gaging stations to develop low-flow statistics at the partial-record stations and ungaged sites by using three methods, the drainage area ratio method, Move1 (a USGS statistical program), and regression analysis using watershed characteristics. A number of other states (Idaho, West Virginia, New Hampshire, Massachusetts, New York, and Pennsylvania) have been using similar methods to develop regional regression equations to calculate some low-flow statistics and presenting this material through StreamStats an existing USGS web based application.

It is proposed that the New Jersey Science Center, in cooperation with the NJDEP, develop a statewide interactive web based application using StreamStats to determine low-flow statistics at ungaged sites, partial-record sites, and retrieve data for long-term continuous streamflow gaging stations.

Approach

The study would be conducted in two phases.  In the first phase, approaches taken in previous studies will be identified and reviewed to determine if these approaches or some modification of them would produce a tool that would satisfy the needs of the NJDEP. Phase 1 would include the review of data needs and availability and the development of a detailed work plan for Phase 2.

The second phase would develop the regional regression equations and incorporate the low-flow regional equations in the New Jersey web based StreamStats application presently being developed for flood-frequency analysis for the NJDEP through a cooperative agreement with the US Army Corps of Engineers. The reason for the two-phase approach is the amount of stream regulation (impacts of surface and ground water diversions) in New Jersey. In the studies referenced above, the analysis was done for streams with little regulation or those that did not have significant low-flow trends. Although it is anticipated that the approaches used in these other studies with possibly some minor modification will be appropriate, the period of record of the streamflow data to be used in the study will require careful consideration to limit human impacts on streamflow. Some of the low flow statistics to be considered are:

- 7 day 10 year low flow (7Q10),

- Monthly 7Q10

- Median of minimum flows for each month for the period of record

Phase 2 would also be designed to take advantage of the results of the flood-frequency project to the extent possible to reduce project costs.

## Objectives

The overall objective of this project is to develop regional peak discharge relations for ungaged drainage basins in New Jersey by evaluating the stream gage data collected from the cooperative New Jersey gage network. The specific study objectives are:

Phase 1

- Review previous studies performed in other states related to the development of regional regression equations for estimating low-flow statistics at ungaged stream sites.

- From the reviewed reports and available information for streams in New Jersey, identify those basin characteristics most likely to be used in equations to calculate low-flow statistics at stream sites,

- Develop a detailed work plan for Phase 2 of the study.

Phase 2 (preliminary)

- .

- Develop the methodology for estimating low-flow statistics for ungaged sites that are above, below or between continuous gaged sites.

- Develop low flow statistics for partial record stations using Move 1

- Develop regional regression equations to estimate specific low-flow statistics for ungaged sites that are not in a watershed with partial or continuous stream gages on non-tidal streams that are not heavily regulated or for time periods that were not heavily regulated in New Jersey.

- Incorporate low-flow statistics at existing gage sites and the low-flow regression equations for ungaged sites into the New Jersey  StreamStats web application..

## Relevance and Benefits

The project will greatly assist the New Jersey agencies, particularly the Department of Environmental Protection (NJDEP) and Transportation (NJDOT), county and municipal government agencies, as well as engineers and planners in the flood-plain management, as well as planning, design, and rehabilitation of dams, culverts and other infrastructure to support statewide growth. This proposal addresses priority issues of the USGS cooperative program by providing information that will help government at all levels deal with flood issues.

This proposal directly addresses USGS Water Resources Memorandum No. 95.44 by “advancing the knowledge of the regional hydrologic system, advancing the understanding of hydrologic processes, providing data useful to multiple parties for planning and operational purposes, and furnishing hydrologic data or information that contributes to protection of life and property”. The results have significant implications for application of the methodologies and understanding gained in this study to similar programs nationally.

Phase 1

Task 1 – Review existing studies from other Science Centers and the work done in for the New Jersey Highlands.

Task 2 – Data needs

- Determine most relevant variables for regression analysis from review of previous studies

- Determine data sources

Task 3 – Review findings with the NJDEP

Task 4- Develop detailed work plan for Phase 2

Task 5 – NJDEP review of Phase 2 work plan

## Approach for Phase 2 (preliminary, depends on results of Phase 1)

The project will use data from the various gaging networks in New Jersey, and portions of the gage networks of nearby Pennsylvania, New York, and Delaware to develop a database for analysis. The data from New Jersey streams, as well as from nearby states will be grouped into similar geographic regions in order to develop 3 or five regional relations to minimize geographic bias. For areas where stream gages exist, a drainage area ratios method will probably be used. The second phase will involve development and documentation of a web site to automate the determination of low flow statistics for gaged and ungaged sites.

Phase 2 (Preliminary work plan for Phase 2)

Task 1 – Project Coordination – Meetings with cooperator and internal

## Task 2 – Collect relevant data identified in Phase 1

The relevant data from each Science Center will be identified. Both continuous and partial record gage data for basins will be retrieved from the District’s database.. Only those gages that are relatively unaffected by regulation at low flow (or an identified low human impact period of record) will be included in the analysis. The database may include:

- USGS station identification number

- USGS gage name

- Latitude and longitude

- Period of record of stream gage

- Drainage area

- Relevant low flow data

## Task 3 – Update basin characteristics (from Phase 1) to be used in regression analysis

A Geographic Information System (GIS) will be used to determine updated basin characteristics for each gage. Some of the basin characteristics that may be used in the analysis are drainage area, basin shape, precipitation, forest cover, percent impervious cover, percent lakes and swamps, underlying geology, and main channel slope. Many of these characteristics have GIS coverages and are in Stream Stats.

Task 4 – Continuous gages, partial record stations, and stream reaches with gages upstream or downstream

- Calculate or import from other studies low flow statistics for continuous gages

- Calculate stream statistics for partial record stations

- Determine stream reaches that will use drainage area ratio method to determine low flow statistics

Task 5 – Perform regression analysis

To reduce the standard error of regression, the State may be divided into 3 or 5 regions based on residual analysis of preliminary statewide regression analysis and geologic maps. Each region will have a separate regression analysis. The relations developed will allow for the estimate of various low flow statistics (to be determined with NJ DEP) at  ungaged site on a stream. , but will not include the main stem of the Delaware River or tidal areas. The models will be completed in two steps; preliminary regression analysis to select significant basin characteristics from those chosen in Task 1; and final regression analysis or verification. The use of the developed equations for stream sites where the explanatory variables are outside the range of the variables used to develop the equations may decrease the accuracy of the calculated statistics.

Task 6 – Science Investigation Report

A Science Investigation Report shall be developed which will include the database used in the analysis, the final regression equations, step by step instructions and associated graphs. The publication will be Web based.

Task 7 – Development of a Web page

The USGS Web page of Stream Stats will be updated to include the low flow statistics, regional equations, and drainage area method to determine low flow statistics at ungaged sites.

## Proposed Project Budget

Assuming a March, 2008 start date, the budget summary by Federal Fiscal Year and project Phase is as follows: (note for internal review – Phase 2 budget includes 11 months Ward Hickman and 6 months for Kara Watson, may be able to cut by one month for each saving approximately 40, 000 on salary)

| Account Description | Phase 1 FY 2008 |
| --- | --- |
| NJDEP Funding | $40,500 |
| USGS Funding |  |
| Total | $40,500 |
| Personnel Costs Salaries including fringe benefits | $19,900 |
| Other Costs direct | $6,600 |
| Reports and StreamStats by other offices |  |
| Total Direct Costs | $26,500 |
| Indirect Costs | $14,000 |

Schedule

| Tasks/Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 1 – review existing studies | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 2 – data needs | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 3 – develop work plan Phase 2 |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 4 – DEP review |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 2 (preliminary) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Task 1 – project coordination |  |  |  |  | X | X | X | X | X | X | X | X | X | X | X | X | X |
| Task 2 – data needs |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| Task 3 – basin characteristics |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |
| Task 4 – low flow stats for continuous gages, partial record stations, and drainage area method |  |  |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |
| Task 5 – Regression equations |  |  |  |  |  |  |  |  |  |  | X | X | X |  |  |  |  |
| Task 6 - Report |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |
| Task 7 – Web Stream Stats |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |  |