Appalachian Plateaus Groundwater Availability Study Water Availability and Use Science Program FY2016 End-of-Year Report
Summary of Work in FY2016 

Contact:
Kurt J. McCoy., Virginia-West Virginia Water Science Center

         
kjmccoy@usgs.gov or 804-261-2656
(1) PROJECT ACCOMPLISHMENTS/CONTRIBUTIONS FY2016
FY2016 activities of the Appalachian Plateaus Groundwater Availability Study supported by the Water Availability and Use Science Program have focused on preparation of hydrogeologic framework study and model results, and presentation of results to various State and Federal agencies.  Highlighted activities in FY2016 include:
· Study website maintained as a central portal of GIS, geohydrologic information, and water related news/links for the Appalachian Plateaus. 

http://va.water.usgs.gov/appalachianplateaus/main.html
· Interactive water budget viewer to highlight water budget results of SIR 2015-5106. 
http://va.water.usgs.gov/appalachianplateaus/sir2015-5106/
· Publication of USGS Data Releases:

· Ladd, D.E., 2016, Mean-annual and mean-seasonal water-budget estimates from a Soil-Water-Balance model of the Appalachian Plateaus, 1980 through 2011, USGS Data Release: http://dx.doi.org/10.5066/F7X06544
· Ladd, D.E., 2016, Hydrogeologic framework bottom elevations and thicknesses of Permian, Upper Pennsylvanian, Lower Pennsylvanian, and Mississippian units in the Appalachian Plateaus Physiographic Province, USGS Data Release: http://dx.doi.org/10.5066/F7ZW1J1Q
· Journal article in review (Geophysical Research Letters):  The Persistence of Saline Groundwater in Late Paleozoic Rocks of the Appalachian Plateaus, by R.M. Yager, K.J. McCoy, C.I. Voss, W.E. Sanford, and R.B. Winston
· In many regions of the world, the shallow (<300 m) subsurface is replenished with meteoric recharge within a few centuries or millennia, but in some regions saline groundwater persists despite sufficient rainfall.  Analysis of the flushing rate of shallow groundwater usually considers the permeability and recharge rate, and a static landscape.  The influence of landscape evolution can become important over millions of years, however.  Here we present numerical simulations of fluid flow and transport in the top 1 km of a sedimentary foreland basin that indicate the rate of uplift and erosion (20 m/Ma) balances that of meteoric flushing.  Paleozoic-age saline groundwater persists at shallow depths that might otherwise contain potable water. Similar hydrogeologic conditions and uplift and erosion rates likely exist in many other regions of the world, where a moving landscape has likely never been considered as an important contributor to groundwater quality.
· Draft of USGS SIR:  Hydrogeologic Framework and Conceptual Model of Permian, Pennsylvanian, and Mississippian Aquifers in the Appalachian Plateaus Physiographic Province
The report focuses on the hydrogeologic framework modeling and updates to conceptual models of the study area.  Major findings to be included in report are as follows:

Hydrogeologic Framework
· New regional aquifer surfaces modeled from oil and gas well data extend beyond depths of saline water
· Permeability is inversely related to topography
Conceptual Model
· Parametric study to identified the range of permeability and anisotropy ratios influencing  the thickness of the fresh groundwater flow system
· Historic oil and gas data used with Archie’s Law to confirm thickness of freshwater aquifer along cross section from eastern highlands to regional drain.
· Saline water at shallow depths is partially a result of erosion rates exceeding the rates of meteoric flushing
· Most freshwater flow occurs in the near surface and is deepest in hillslope environments
· Regional flow is limited by water-table boundary and high anisotropy
(2) PROJECT WORK PLAN and BUDGET FY2017 
· Planned project end in FY2016.   
(3) NOTEWORTHY COLLABORATIONS, MEETINGS, and TECHNICAL TRANSFER ACTIVITIES, FY2016 
Abstract/Presentations of results for the Appalachian Plateaus Groundwater Availability Study 
1. Water Conference of the Virginias, Stonewall Jackson Lake, WV, October 5-6, 2015.

a. McCoy, K.J. – “Groundwater discharge to streams in mountainous regions of the Eastern US”
b. McCadoo, M. – “Use of borehole geophysical logs to determine fracture distribution and water occurrence in wells of Appalachian Plateaus”

2. 2015 Geological Society of America National Meeting, Baltimore, MD, Nov. 1-4, 2015.
a. Yager, R. – “The persistence of saline water in late Paleozoic rocks of the Appalachian Plateaus”
b. McCoy, K. – “Groundwater discharge to streams in mountainous regions of the Eastern US”

3. USGS Saline Water Resources Workshop, Denver CO, Nov. 18-19, 2015
a. McCoy, K. – “Mapping and characterization of shallow saline waters”

b. Williams, J – “Fluid property logs and geophysical induction surveys in Appalachian oil and gas fields”

4. Invited Speaker – West Virginia University, School of Natural Resources, Morgantown WV, Feb. 8, 2016
McCoy, K. – “Groundwater discharge to streams and relevance to ecosystem flows in the Appalachian Plateaus”
5. National Groundwater Association, Groundwater from mountains in to the sea in the Central Atlantic Region, Virginia Beach, VA, June 6-7, 2016
Nelms, D – “Groundwater discharge to streams in the Eastern US”
6. USGS National Groundwater Meeting, Reno NV, Aug 29- Sept 2, 2016
a. McCoy, K. – “Dynamic groundwater discharge to streams and relevance to understanding stream chemistry in Appalachian Plateaus”

b. Williams, J – “Bridging the Gap – Geophysical Log Analysis of the Fresh-Saline Water Transition in the Fractured Bedrock above the Marcellus Shale Gas Play”
(4) REPORT PRODUCTS AND BIBLIOGRAPHIC UPDATE, FY2016 
· Ladd, D.E., 2016, Mean-annual and mean-seasonal water-budget estimates from a Soil-Water-Balance model of the Appalachian Plateaus, 1980 through 2011, USGS Data Release: http://dx.doi.org/10.5066/F7X06544
· Ladd, D.E., 2016, Hydrogeologic framework bottom elevations and thicknesses of Permian, Upper Pennsylvanian, Lower Pennsylvanian, and Mississippian units in the Appalachian Plateaus Physiographic Province, USGS Data Release: http://dx.doi.org/10.5066/F7ZW1J1Q
(5) ACKNOWLEDGMENTS and TESTIMONIALS, FY2016
Please refer to letters of support from previous years.
(6) PROJECT TEAM DIRECTORY, FY2016
Kurt J. McCoy

Affiliation: USGS-WRD

Location: VA Water Science Center

Phone: 804-261-2656
Email: kjmccoy@usgs.gov

Role:  Project Chief
Richard Yager

Affiliation: USGS-WRD

Location: NY Water Science Center

Phone: 607-266-0217 x3004
Email: ryager@usgs.gov

Role: Lead Modeler

Mark Kozar

Affiliation: USGS-WRD

Location: WV Water Science Center

Phone: 304-347-5130 x 234
Email: mdkozar@usgs.gov

Role: Water Budget Analysis
David Nelms

Affiliation: USGS-WRD

Location: VA Water Science Center

Phone: 804-261-2630
Email: dlnelms@usgs.gov

Role:  Water Budget Analysis
David Ladd

Affiliation: USGS-WRD

Location: TN Water Science Center

Phone: 615-837-4773
Email: deladd@usgs.gov

Role:  GIS Support
Jack Monti
Affiliation: USGS-WRD

Location: NY Water Science Center

Phone: 631-736-0783
Email: jmonti@usgs.gov

Role:  Water Use/Web development
Mike Pantea

Affiliation: USGS-GECSC
Location: Geoscience and Environmental Change Science Center
Phone: 303-236-5554
Email: mpantea@usgs.gov

Role:  Geologic modeling
(7) PHOTOS and RESULTS GRAPHICS, FY2016
One primary goal of FY2016 efforts was to publish results of modeling to define the depth of freshwater circulation and assess local vs regional flow.  


[image: image1.emf]

[image: image2]

[image: image3.emf]

[image: image4]
Figure 1. The Appalachian Plateaus have been highly dissected by stream erosion. A thin skin of stress-relief fractures at land surface diverts most recharge to local drainages through the weathered bedrock (thicker blue arrows), while deeper groundwater flows to major lowland valleys (thinner arrows). Salinity levels estimated from borehole geophysical logs (Supporting Information S2) are color-coded by ranges shown on section. Freshwater 100 to 200 m thick is separated from underlying saline water and brine by a mixing zone. 





Figure 2. Average freshwater thickness in upland recharge areas as a function of permeability of the unweathered bedrock and the uplift/erosion rate. Higher values of permeability and lower erosion rates yield deep meteoric flushing and thick freshwater aquifers, while the reverse yields little flushing and shallow saline water. A narrow range of permeability and erosion rates values produces the 100 to 200-m-thick freshwater aquifers observed in borehole geophysical logs. Average freshwater thickness was computed over a 13-km section centered on well A. Reported ranges of permeability [Freeze and Cherry, 1979] for sandstone and shale lithologies and global, basin-scale erosion rates [Portenga and Bierman, 2011] are given for comparison.








PAGE  
6

_1536413060.pdf


 
Regional flow system: 10’s of km’s


Local flow system: km’s


freshwater: 
100-200 m


< 1 g/L


Vertical exageration approximately 40x


weathered 
bedrock:
15 to 50 m


alluvium


groundwater
flow


saline water and brine:
> 10 g/L


Ohio River


upland
valley


 


 


mixing zone:
1 to 10 g/L


0


60


120


180


240


300


360


420


480


DS (g/L)


Well 8
D


ep
th


, i
n 


m
et


er
s D
ep


th
, i


n 
m


et
er


s


0


60


120


180


100100.1 1


100100.1 1


DS (g/L)


Well 2






_1536413062.pdf


Uplift/Erosion rate, in m/Ma


0 10 20 30 40 50


Pe
rm


ea
bi


lit
y,


 in
 m


2


10-18


10-17


10-16


10-15


DEEP METEORIC 
FLUSHING


Appalachian
Plateaus


600 m


500 m


400 m


300 m


200 m


100 m


50 m


Sa
nd


st
on


e
Sh


al
e


SHALLOW FRESHWATER


 AQUIFERS


LITTLE METEORIC 
FLUSHING


0


60


120


180


Fr
eq


ue
nc


y
 o


f r
at


es






