Water Availability and Use Science Program

Upper Rio Grande Basin Focus Area Study

FY 2016 End-of-Year Report

January 5, 2017

(1) PROJECT ACCOMPLISHMENTS/CONTRIBUTIONS (FY 2016)

The Upper Rio Grande Basin (URGB) Focus Area Study (FAS) has completed the first year of the projected three-year project.  All project components are underway and on schedule; none have been completed to date.  No publications are in press.

The following section summarizes accomplishments from each project component from FY 2016.

Water Use

Available water-use data from the USGS water-use compilations for Colorado, New Mexico, and Texas (1985-2015), other completed studies, and new approaches are being assessed to evaluate water use and withdrawal trends in the URGB.

Data for each major water-use category (public supply, self-supplied domestic, self-supplied industrial, commercial, thermoelectric, livestock, mining, aquaculture, irrigation, hydroelectric, and wastewater) in the CO, NM, and TX portions of the URGB for the years 1985, 1990, 1995, 2000, 2005, and 2010 are being re-aggregated from a county basis to a watershed basis at the eight-digit hydrologic unit code (HUC-8) scale.  This work is complete for CO and TX, and is nearly complete for NM.  Categories that remain in NM are irrigation, livestock, self-supplied industrial, commercial, and mining.  The compilation for 2015 is underway in all three states – CO currently has wastewater, self-supplied industrial, and hydroelectric categories in review.

Metered withdrawal data for self-supplied domestic residences were requested from the NM Water Rights Bureau in an effort to generate more-accurate State-wide domestic per-capita values.

A new semi-automated method was developed to produce a vector feature class of irrigated agricultural field boundaries using 2014 aerial imagery data from the National Agriculture Imagery Program (NAIP) and ESRI ArcGIS tools. Preliminary polygons representing the boundaries of agricultural fields in the URGB have been generated from Albuquerque, NM to the southern boundary of the study area in Texas and Mexico.  Field boundaries for the Colorado portion of the URGB were previously completed and provided by the Rio Grande Water Conservation District.

Evapotranspiration

Evapotranspiration (ET) from irrigated croplands and native vegetation (e.g., riparian ecosystems) is a significant component of the water budget in the Western U.S. Remote sensing can provide useful, spatially-distributed information and has important advantages over statistical interpolation between ET flux towers and climate stations, or estimates made from indirect proxies, like consumption of electricity by irrigation pumps.

The Operational Simplified Surface Energy Balance (SSEBop) model was used to estimate actual ET for the URGB.  Land surface temperature from 780 Landsat images (over 17 path/rows), air temperature from the TopoWx, and potential ET from GRIDMET, which used data from the North American Land Data Assimilation System (NLDAS), were used to calculate monthly and annual actual ET at a 100-m resolution throughout the URGB.  Several ET flux towers within the URGB have been identified for use in calibrating the model results, particularly for mountain forest areas.

Groundwater

Water enters the primary URGB aquifer, known as the Santa Fe Group, from mountain front recharge and seepage from the Rio Grande, its tributaries and adjacent conveyance structures, and excess irrigation. If groundwater pumpage from an aquifer exceeds recharge, water levels in the aquifer decline, as has been observed throughout the URGB. These declining water levels can have adverse effects on long-term groundwater availability and sustainability, water quality, and land subsidence.

Existing data on hydrogeologic basin boundaries, cross sections, structure (tops and bases of hydrogeologic units) and hydraulic properties are being compiled from the published literature.  Structural basin boundaries are being digitized and entered into a geodatabase, cross-sections are being compiled in a georeferenced 3-D imaging platform and evaluated, and hydraulic properties are being extracted and compiled in tables. A hydrostratigraphic section (strat map) is being developed for each of the sub-basins that comprise the URGB.

Snow Processes

Snowmelt may contribute 70-80% of annual runoff in the western U.S. and is critically important to water availability in the URGB. Reservoirs capture and distribute snowmelt runoff to meet water supply demands of the Basin and legal requirements of the Compact. Better understanding is needed of the processes that influence water yield from snowpack to improve the ability of water managers to plan for changes in the timing and availability of snowmelt-derived water resources.

Four enhanced meteorological stations were installed in the Basin and snow surveys were conducted to improve the interpretation of existing SNOTEL data and advance snowpack and snowmelt modeling.  Other historical data have been compiled to facilitate a physically based snow modeling effort.

Streamflow Processes

It is important to think of groundwater and surface water as a single, connected resource. Baseflow, or the groundwater contribution to streams, is critical to sustaining streamflow in the URGB. But the timing and availability of spring runoff is changing, which may substantially affect the way surface water must be managed.

Stream chemistry data from 19 sites in the URGB above Elephant Butte Reservoir had long-term records meeting a stringent set of criteria that allowed their use to partition baseflow and direct surface-runoff contributions to streamflow.  Preliminary results indicated that baseflow was a substantial fraction of streamflow throughout the URGB, but that fraction varied widely across the Basin.

Watershed processes

Hydrologic simulation models provide a useful tool to assess the effects of different watershed management alternatives on water resource availability and timing. Data and results from water use, ET, snow process, and streamflow process components of this study will be integrated using a regional calibration of the Precipitation-Runoff Modeling System (PRMS) to allow simulation of the impacts of land-use and climate change.

Climate, soils, topographic, land-use, and land-management information is being compiled for the URGB.  The PRMS model will be built, tested, and run in the coming year.

Study Results Visualization

The creation of a new, public-facing website and mapping application could be extremely valuable to the community of professionals managing and monitoring water resources in the URGB. This new web presence intends to provide access to water data available for the URGB and access to research products stemming from the URGB FAS.

A project website was constructed (https://txpub.usgs.gov/projects/urgb_fas/) as the communication vehicle for project information to our stakeholders. The website currently is live with basic project information, real-time maps, methods descriptions, timeline, and expected deliverables.

(2) PROJECT WORKPLAN AND BUDGET FOR FY 2017

The URGB FAS will quantify and assess spatial distribution and temporal trends of selected water-budget components. Specific objectives include (a) assessing water-use data by category for 1985-2015 at the HUC-8 scale; (b) quantifying actual evapotranspiration using the remote-sensing-based Simplified Surface Energy Balance method; (c) assessing groundwater availability through a basin-scale hydrogeologic framework and water-level surface and change maps; (d) modeling snow processes in URGB headwaters; (e) characterizing streamflow processes through trend analysis and automated hydrograph and hydrochemical baseflow separation methods; (f) integrating water-budget components using a PRMS watershed model; and (g) summarizing results in publically displayed interactive web maps.

The original work plan (November 19, 2015) has undergone minor revisions to reflect stakeholder input and changes to project staff.  Changes include:

- increased emphasis on snow process data collection to support the modeling effort,

- additional capacity in watershed modeling as a vehicle to integrate study water-budget components at refined sub-watershed scale,

- increased emphasis on use of observed ET data to ground-truth SSEB ET estimates,

- decreased emphasis on field-based surveys to verify field crop types and irrigation methods,

- additional capacity in automated digital delineation of irrigated agricultural areas, and

- decreased effort to assess self-supplied domestic water use.

In support of objectives listed above, the following approaches and activities are planned for FY17.

Water Use

The NM Office of the State Engineer (NM OSE) has indicated that the NM 2015 compilation will not be available for the March 2017 USGS deadline.  The USGS will discuss options for assisting NM OSE with the NM State compilation.  Data for TX should be available by January 2017.

Metered withdrawal data for self-supplied domestic residences were requested from the NM Water Rights Bureau in an effort to generate more-accurate State-wide domestic per-capita values.

Edit the preliminary polygons of irrigated agricultural field boundaries (Albuquerque, NM to the southern boundary of the study area in Texas and Mexico) for errors.  This part of the task generally is not automated, and may take some time.  Use the semi-automated tool to produce irrigated field boundaries from Albuquerque to the Colorado border. Data from the 2015 USDA Cropland Data Layer (CDL) and similar data from Instituto Nacional de Estadística y Geografía (INEGI, Mexico) will be used to assign a preliminary crop type to each field.

Evapotranspiration

Data from ET flux towers within the URGB will be used to calibrate SSEBop model results, particularly for mountain forest areas.

Groundwater

Continue compiling existing data on hydrogeologic basin boundaries, cross sections, structure (tops and bases of hydrogeologic units) and hydraulic properties from the published literature.  Continue digitizing structural basin boundaries and entering data into a geodatabase, compiling and evaluating cross-sections in a georeferenced 3-D imaging platform, and extracting and compiling hydraulic properties in tables. Develop a hydrostratigraphic section (strat map) for each of the sub-basins that comprise the URGB.

Cross-sections will be developed for sub-basins that have enough existing structural data but do not have a current cross section.  Water-level altitude maps will be constructed for sub-basins that have ample water-level data.  Currently the time period for the water-level maps is 1985-2015; availability of data will determine actual time period for water-level maps.  Geostatistical methods will be used to analyze ground-water-level status and trends, with particular attention to discontinuities between groups of wells over space and time.  Also, work will start on the estimation of water in storage and change in storage tasks this fiscal year.  The team has started acquiring existing groundwater flow models. The existing groundwater flow models will be used for the storage estimation task only.

Snow Processes

Researchers will use data collected in project year 1 and other historical data within a physically based snow model to improve our understanding of the influence of climate, land cover, topography, and other factors on snow processes in the URGB.  Model results will be used to quantify snow water resources in the URGB and determine how representative existing SNOTEL measurements are of snowmelt in the Basin.

Streamflow Processes

Refine preliminary chemical baseflow separation results, which indicated that baseflow was a substantial fraction of streamflow throughout the URGB, but that fraction varied widely across the Basin. Complete traditional streamflow hydrographic baseflow separation analysis for comparison with chemical baseflow analysis. Assess how baseflow relates to watershed characteristics, and explore variability and trends in baseflow across the Basin and over time.

Watershed processes

Build, test, and run a PRMS model for the URGB.  Use a coarser-resolution (e.g., HUC-8) at the Basin scale to provide a framework to integrate the separate water-balance components from this study. Use a finer-resolution (e.g., HUC-12) for the northern URGB to capture and integrate the effects of snow, baseflow, ET, and other processes on native flows in headwater watersheds.

Study Results Visualization

The project website (https://txpub.usgs.gov/projects/urgb_fas/) will be enhanced with updated project information and results; links to data and other products, state Water Science Center websites, National Water Census website, and other useful resources; a full-frame mapping application to show final geospatial data products; and direct connection to ScienceBase for released/final data products.

Budget for FY17

The URGB FAS requests $500,000 to support project activities in FY2017 (Table 1).  The total amount is unchanged from the original project work plan.

Table 1. Estimated FY2017 funding for URGB FAS, itemized by Water Science Center and project component.

| Water Science Center Project Component | Salary | Travel | Total |
| --- | --- | --- | --- |
| NM WSC – Albuquerque Project Management, Water Use, Watershed Processes | $146,000 | $25,000 | $171,000 |
| CO WSC – Pueblo Water Use | $30,000 | $0 | $30,000 |
| TX WSC – Austin Water Use | $30,000 | $0 | $30,000 |
| TX WSC – Austin Groundwater | $100,000 | $0 | $100,000 |
| TX WSC – Austin Data & Study Results Visualization, Data Management | $25,000 | $0 | $25,000 |
| CO WSC – Denver Snow Processes | $105,000 | $5,000 | $110,000 |
| UT WSC – Salt Lake City Streamflow Processes | $34,000 | $0 | $34,000 |
| TOTAL | $470,000 | $30,000 | $500,000 |

(3) NOTEWORTHY COLLABORATIONS, MEETINGS, TECHNICAL TRANSFER ACTIVITIES, SPIN-OFF PROJECT DEVELOPMENTS, AND ACKNOWLEDGEMENTS

In the work plan development phase, the URGB FAS team engaged stakeholders with presentations and discussion of proposed project activities.  The following meetings were held: Water Management Area Investigators Chief Meeting (February 10, 2015), U.S. Bureau of Reclamation (February 18, 2015), Rio Grande Water Conservation District (February 19, 2015), Rio Grande Compact Commission Engineer Advisors (February 23, 2015), and U.S. Army Corps of Engineers.  The URGB FAS kickoff meeting was held March 10-11, 2015 in Albuquerque, NM with project personal and stakeholder participation.

After the development of the Draft Work Plan (July 1, 2015), two initial stakeholder meetings were held in Santa Fe, NM (September 22, 2015) and El Paso, TX (September 24, 2015).  Substantive changes and additions to the FAS scope included a decreased emphasis on ecoflows and an increased emphasis on snow processes and ET quantification.  The Final Work Plan was revised October 1, 2015 and made public on February 10, 2016.

In the next fiscal year, project updates will be presented at the New Mexico Water Conference (October 6, 2016) and other workshops and conferences.  Stakeholders and project personnel will participate in the URGB FAS Project Annual Meeting and Forum (November 8-9, 2016, Albuquerque, NM).  Project personnel will meet and discuss project progress and refined scope with stakeholders during formal meetings with individual agencies as well as informal meetings, as the opportunity arises.

(4) Report Products, Bibliographic Update, Data Releases, and Model Archives

The project just completed the first year of a three-year study and currently does not have any published report products, bibliographic updates, data releases, or model archives.

(5) PROJECT TEAM DIRECTORY

Upper Rio Grande Basin Focus Area Study

Kyle Douglas-Mankin, USGS New Mexico Water Science Center, Albuquerque NM; kdouglas-mankin@usgs.gov; 505-830-7916; Project Lead.

Water Use

Tammy Ivahnenko, USGS Colorado Water Science Center, Pueblo, CO; ivahnenk@usgs.gov; 719-562-2848; Project Component Lead: Water Use.

Natalie Houston, USGS Texas Water Science Center, Austin, TX; nhouston@usgs.gov; 512-927-3565; Water Use Specialist for TX

Amy Galanter, USGS New Mexico Water Science Center, Albuquerque, NM; agalanter@usgs.gov; 505-830-7939; Water Use Specialist for NM

Whitney Lentz, USGS Colorado Water Science Center, Pueblo, CO; wlentz@usgs.gov; 719-562-2866; Student Contractor

Amanda Rothermal, USGS Colorado Water Science Center, Pueblo CO; arothermal@usgs.gov; 719-562-2867; Student Contractor/Compiler for the CO 2015 Compilation

Diana Pedraza, USGS Texas Water Science Center, San Antonio, TX; dpedraza@usgs.gov; 210-691-9237; Geographer, Geospatial development of a semi- automated method to delineate irrigated acres in the URGB

Victoria Stengel, USGS Texas Water Science Center, Austin, TX; vstengel@usgs.gov; 512-927-3571; Geographer, Geospatial development of a semi- automated method to delineate irrigated acres in the URGB

David Andresen, USGS Texas Water Science Center, Austin, TX; dandresen@usgs.gov; 512-927-3530; Geographer, Python programmer, assisting with the Irrigated Acres task

Evapotranspiration

Gabriel Senay, USGS Earth Resource Observation and Science (EROS) Center, Fort Collins, CO; senay@usgs.gov; 605-594-2758; Project Lead, Project Component Lead: Evapotranspiration, geospatial ET modeling using remote sensing data.

Groundwater

Natalie Houston, USGS Texas Water Science Center, Austin, TX; nhouston@usgs.gov, 512-927-3565; Project Component Lead: Groundwater, working on all GW tasks

Jonathan Thomas, USGS Texas Water Science Center, Fort Worth, TX; jvthomas@usgs.gov, 682-316-5036; Geophysicist working on structure, cross-sections, and water level maps

Daniel Tebo, USGS Texas Water Science Center, Austin, TX; dtebo@usgs.gov, 512-927-3537; Student Trainee Hydrology assisting with structure and cross sections

Diana Pedraza, USGS Texas Water Science Center, San Antonio, TX; dpedraza@usgs.gov, 210-691-9237; Developing geodatabase containing structural basin boundaries

Toby Welborn, USGS Texas Water Science Center, Portland, OR; tlwelbor@usgs.gov, 503-251-3287; Working on water level status and trends task

Linzy Foster, USGS Texas Water Science Center, Austin, TX; lfoster@usgs.gov, 512-927-3529; Groundwater flow modeler, scheduled to work on estimating water in storage and change in storage from existing GW flow models in FY 2018, however has some time available this year and we are going to get started on this task later on in the year

Snow Processes

Graham Sexstone, USGS Colorado Water Science Center, Lakewood, CO; sexstone@usgs.gov, 303-236-6878; Project Component Lead: Snow Processes, hydrologist working on all snow tasks.

Colin Penn, USGS Colorado Water Science Center, Lakewood, CO; cpenn@usgs.gov, 303-236-6952; Hydrologist assisting with historical data compilation, GIS geodatabase development, and field work.

David Clow, USGS Colorado Water Science Center, Lakewood, CO; dwclow@usgs.gov, 303-236-6881; Research Hydrologist assisting with workplan development and manuscript preparation.

Streamflow Processes

Matt Miller, USGS Utah Water Science Center, Salt Lake City, UT; mamiller@usgs.gov; 801-908-5065; Project Component Lead: Streamflow Processes. Assist with surface water processes tasks.

Christine Rumsey, USGS Utah Water Science Center, Salt Lake City, UT; crumsey@usgs.gov; 801-908-5022; Complete streamflow processes tasks, and collaborate with other project components to integrate results across the FAS.

Watershed Processes

Kyle Douglas-Mankin, USGS New Mexico Water Science Center, Albuquerque NM; kdouglas-mankin@usgs.gov; 505-830-7916; Project Component Lead: Watershed Process.

C. David Moeser, USGS New Mexico Water Science Center, Albuquerque NM; cmoeser@usgs.gov; 801-908-5022; Watershed model development, testing, and analysis.

Study Results Visualization

Daniel Pearson, USGS Texas Water Science Center, Austin, TX; dpearson@usgs.gov, 512-927-3561; Project Component Lead: Study Results Visualization, website development and communication

Justin Hoegenauer, USGS, Texas Water Science Center, Austin, TX; jhoegenauer@usgs.gov, 512-927-3500; Website development and communication

Data Management

Diana Pedraza, USGS Texas Water Science Center, San Antonio, TX; dpedraza@usgs.gov, 210-691-9237; Project Component Lead: Data Management.

(6) PHOTOS, ANIMATIONS, AND GRAPHICS

The project website (https://txpub.usgs.gov/projects/urgb_fas/) will provide access to photos, animations, graphics, reports, maps, and other products of this study.  The website is currently live and efforts are ongoing to populate the site with current project information, results, links, and products.