Water Availability and Use Science Program

Upper Rio Grande Basin Focus Area Study

FY 2017 End-of-Year Report

September 1, 2017

(1) PROJECT ACCOMPLISHMENTS/CONTRIBUTIONS (FY 2017)

The Upper Rio Grande Basin (URGB) Focus Area Study (FAS) has completed the second year of the projected three-year project.  All project components are on schedule; none have been completed to date.  No publications are in press.

The following section summarizes accomplishments from each project component from FY 2017.

Water Use

Available water-use data from the USGS water-use compilations for Colorado, New Mexico, and Texas (1985-2015), other completed studies, and new approaches are being assessed to evaluate water use and withdrawal trends in the URGB.

Data for each major water-use category (public supply, self-supplied domestic, self-supplied industrial, commercial, thermoelectric, livestock, mining, aquaculture, irrigation, hydroelectric, and wastewater) in the CO, NM, and TX portions of the URGB for the years 1985, 1990, 1995, 2000, 2005, and 2010 have been re-aggregated from a county basis to a watershed basis at the eight-digit hydrologic unit code (HUC-8) scale.  The compilation for 2015 is nearly complete.  Water use category trends were analyzed and quality assured for all categories at the HUC-8 level from 1985 to 2010 using graphical summary (choropleth) maps.

A new semi-automated method was developed to produce a vector feature class of irrigated agricultural field boundaries using 2015 aerial imagery data from the National Agriculture Imagery Program (NAIP) and ESRI ArcGIS tools. A complete set of agricultural field polygons in New Mexico and Texas was generated using geoprocessing methods supplemented by manual digitization.  Field boundaries for the Colorado portion of the URGB were previously completed and provided by the Rio Grande Water Conservation District. Crop type assignment was completed using a combination of the USDA Cropland Data layer (or similar data from Instituto Nacional de Estadística y Geografía (INEGI, Mexico)), manual crop assignments, and an accuracy assessment. Irrigated acres for golf courses within the RGB are being digitized from satellite images, and this data layer will be included with the crop irrigated acres in the evapotranspiration (ET)/ consumptive use calculations.

Evapotranspiration

Evapotranspiration (ET) from irrigated croplands and native vegetation (e.g., riparian ecosystems) is a significant component of the water budget in the Western U.S. Remote sensing can provide useful, spatially-distributed information and has important advantages over statistical interpolation between ET flux towers and climate stations, or estimates made from indirect proxies, like consumption of electricity by irrigation pumps.

The Operational Simplified Surface Energy Balance (SSEBop) model was used to estimate actual ET for the URGB.  Land surface temperature from 780 Landsat images (over 17 path/rows), air temperature from the USGS TopoWx, and potential ET from GRIDMET, which used data from the North American Land Data Assimilation System (NLDAS), were used to calculate monthly and annual actual ET at a 100-m resolution throughout the URGB for 2015.  Six ET flux towers within the URGB were used to validate SSEBop, particularly for mountain forest areas. Work is nearly complete to calculate monthly, 100-m, actual ET for the entire URGB for the period 1984 to 2014.

Groundwater

Water enters the primary URGB aquifer, known as the Santa Fe Group, from mountain front recharge, seepage from the Rio Grande, its tributaries and adjacent conveyance structures, and seepage of excess irrigation. Groundwater pumpage has exceeded recharge, causing groundwater levels to decline throughout the URGB, with adverse effects on long-term groundwater availability and sustainability, water quality, and land subsidence.  The FAS is synthesizing disparate studies to develop a basin wide hydrogeologic framework, and assessing current status and recent trends in groundwater levels.

Using data from literature, structural groundwater basin boundaries have been digitized and entered into a geodatabase, cross-sections have been compiled (and constructed, where possible) in a georeferenced 3-D imaging platform and evaluated, and hydraulic properties have been extracted and compiled in tables. A hydrostratigraphic section (“strat map”) is being developed for each of the sub-basins that comprise the URGB.

Snow Processes

Snow water resources are of critical interest to URGB stakeholders. Snowmelt may contribute 70-85% of annual runoff in the western U.S. and is critically important to water availability in the URGB. Reservoirs capture and distribute snowmelt runoff to meet water supply demands of the Basin and legal requirements of the Rio Grande Compact.

This Focus Area Study integrates field measurements, remote sensing, and modeling to improve our understanding of the influence of climate, land cover, topography, and other factors on snow processes in the URGB. Results will provide a better understanding of the processes that influence water yield from snowpack and improve the ability of water managers to plan for changes in the timing and availability of snowmelt-derived water resources.

Four new enhanced meteorological stations were maintained in the Basin and two snow surveys were conducted in 2017. Data will be used to improve the interpretation of existing National Resource Conservation Service Snow Telemetry (SNOTEL) data and advance snowpack and snowmelt modeling.  Peak snow water equivalent depth at four study sites were below average in 2016 and above average in 2017. However, both years had faster, earlier melt outs than average, which presents challenges for water management and planning. Data for the models SnowModel (WY2016) and Precipitation-Runoff Modeling System (PRMS) (1980-2014) were compiled, a script was developed to format weather input data, and preliminary runs were completed. Initial SnowModel runs indicated that SNOTEL observations are comparable to simulated basin-average winter precipitation but overestimate both the simulated basin-average snow water equivalent and snowmelt rate.

Streamflow Processes

It is important to think of groundwater and surface water as a single, connected resource. Baseflow, or the groundwater contribution to streams, is critical to sustaining streamflow in the URGB. However, the timing and availability of spring runoff is changing, which may substantially affect the way surface water must be managed.

Baseflow ranged from 24% to 59% of streamflow for 19 sites in the URGB that met the stringent criteria needed to apply a novel chemical baseflow separation technique.  Preliminary analysis of four automated USGS graphical hydrograph separation methods found only one that was promising, perhaps indicating limitations in applying the standard methods for semi-arid URGB conditions.  Using chemical baseflow results to calibrate graphical baseflow methods would be an important scientific contribution and allow accurate baseflow estimates for other streamgage sites in the region that don’t meet the stringent criteria.

Watershed processes

Hydrologic simulation models provide a useful tool to assess the effects of different watershed management alternatives on water resource availability and timing. Data and results from water-use, ET, snow-process, and streamflow-process components of this study will be integrated using a regional calibration of the PRMS to allow simulation of the impacts of land-use and climate change.

The PRMS model framework of about 1400 hydrologic response units (HRUs) has been constructed for the entire URGB.  Climate, soils, topographic, land-use, and land-management information have being compiled for each HRU.  Ten sub-basins with streamflow gages distributed across the URGB were identified as “native basins” and a basin-wide ET dataset has been compiled for use in calibrating PRMS.

Study Results Visualization

The creation of a new, public-facing project website and mapping application is expected to be extremely valuable to the community of professionals managing and monitoring water resources in the URGB. This new web presence intends to provide access to water data available for the URGB and access to research products stemming from the URGB FAS.

A project website was constructed (https://txpub.usgs.gov/projects/urgb_fas/) as the communication vehicle for project information to our stakeholders. The website currently is live with basic project information, real-time maps, methods descriptions, timeline, and expected deliverables.

(2) PROJECT WORKPLAN AND BUDGET FOR FY 2018

The revised URGB FAS workplan (January 5, 2017) calls for the following specific objectives: (a) assessing water-use data by category for 1985-2015 at the HUC-8 scale; (b) quantifying actual evapotranspiration using the remote-sensing-based Simplified Surface Energy Balance method; (c) assessing groundwater availability through a basin-scale hydrogeologic framework and water-level surface and change maps; (d) modeling snow processes in URGB headwaters; (e) characterizing streamflow processes through trend analysis and automated hydrograph and hydrochemical baseflow separation methods; (f) integrating water-budget components using a PRMS watershed model; and (g) summarizing results in publically displayed interactive web maps.

In support of the objectives listed above, the following approaches and activities are planned for FY 2018.

Water Use

The NM Office of the State Engineer (NM OSE) was not able to complete the New Mexico 2015 compilation by the March 2017 USGS deadline, so the FAS team assisted NM OSE.  Work will be completed and wrapped into the 1985-2015 analysis of trends. The water use results will be integrated with other study components.

Evapotranspiration

Work will be completed to calculate monthly, 100-m, actual ET for the entire URGB for 1984 to 2015.  Actual ET data from SSEBop will be used to validate ET processes in the PRMS watershed model.  Actual ET data from SSEBop will also be compared with existing state consumptive use estimates. The ET results will be integrated with other study components.

Groundwater

Work will be completed on the hydrogeologic framework for the URGB including publishing a Data Release of digital boundaries of alluvial basins, hydraulic properties, and compiled water level data. Water-level altitude maps and water-level change maps for subbasins that have ample data to construct maps will be completed.  Current time period covered in this objective is 1985-2015; availability of data will determine actual time period for water-level maps.  Geostatistical methods will be used to analyze ground-water-level current status and historical trends, with particular attention to discontinuities between groups of wells over space and time, which indicate barriers to flow between wells, changes in withdrawals, or other factors.  Storage parameters from existing groundwater flow models will be used to compute aquifer storage volume and changes in storage volume from water level data. The groundwater results will be integrated with other study components.

Snow Processes

Researchers will use data collected in project years 1 and 2, and other historical data to parameterize SnowModel.  Model results will be used to quantify snow water resources in the URGB and determine how representative existing SNOTEL measurements are of snowmelt in the Basin. Results will be summarized and provided in ScienceBase. The snow process results will be integrated with other study components.

Streamflow Processes

Refine preliminary chemical baseflow separation results, which indicated that baseflow was a substantial fraction of streamflow throughout the URGB, but that the fraction varied widely across the Basin. Complete traditional streamflow hydrographic baseflow separation analysis for comparison with chemical baseflow analysis. Assess how baseflow relates to watershed characteristics, and explore variability and trends in baseflow across the Basin and over time. The streamflow results will be integrated with other study components.

Watershed processes

The PRMS model will be sequentially calibrated for ET processes and streamflow in native basins.  Calibrations of PRMS snow-process parameters from the Rio Grande Headwaters from a parallel study will be applied to the snow regions of the URGB.  Weather forcing data will be used with the calibrated model to simulate long-term trends in water-budget elements, such as soil moisture and native streamflow.

Study Results Visualization

The project website (https://txpub.usgs.gov/projects/urgb_fas/) will be enhanced with updated project information and results; links to data and other products, state Water Science Center websites, National Water Census website, and other useful resources; a full-frame mapping application to show final geospatial data products; and direct connection to ScienceBase for released/final data products.

Budget for FY 2018

The URGB FAS requests $500,000 to support project activities in FY 2018 (Table 1).  The total amount is unchanged from the original project work plan.

Table 1. Estimated FY 2018 funding for URGB FAS, itemized by Water Science Center and project component.

| Water Science Center Project Component | Salary | Travel | Total |
| --- | --- | --- | --- |
| NM WSC – Albuquerque Project Management, Water Use, Watershed Processes | $101,000 | $10,000 | $111,000 |
| CO WSC – Pueblo Water Use | $ | $0 | $25,000 |
| TX WSC – Austin Water Use | $30,000 | $0 | $30,000 |
| TX WSC – Austin Groundwater | $174,000 | $0 | $174,000 |
| TX WSC – Austin Data & Study Results Visualization, Data Management | $55,000 | $0 | $55,000 |
| CO WSC – Denver Snow Processes | $80,000 | $0 | $80,000 |
| UT WSC – Salt Lake City Streamflow Processes | $25,000 | $0 | $25,000 |
| TOTAL | $490,000 | $10,000 | $500,000 |

(3) NOTEWORTHY COLLABORATIONS, MEETINGS, TECHNICAL TRANSFER ACTIVITIES, SPIN-OFF PROJECT DEVELOPMENTS, AND ACKNOWLEDGEMENTS

In the work plan development phase, the URGB FAS team engaged stakeholders with presentations and discussion of proposed project activities.  The following meetings were held: Water Management Area Investigators Chief Meeting (February 10, 2015), U.S. Bureau of Reclamation (February 18, 2015), Rio Grande Water Conservation District (February 19, 2015), Rio Grande Compact Commission Engineer Advisors (February 23, 2015), and U.S. Army Corps of Engineers.  The URGB FAS kickoff meeting was held March 10-11, 2015 in Albuquerque, NM with project personnel and stakeholder participation.

After the development of the Draft Work Plan (July 1, 2015), two initial stakeholder meetings were held in Santa Fe, NM (September 22, 2015) and El Paso, TX (September 24, 2015).  Substantive changes and additions to the FAS scope included a decreased emphasis on ecoflows and an increased emphasis on snow processes and ET quantification.  The Final Work Plan was revised October 1, 2015, made public on February 10, 2016, and revised slightly on January 5, 2017.

In FY 2017, URGB FAS staff led and participated in a total of fifteen stakeholder meetings, presentations, and workshops.  Stakeholders and project personnel participated in the URGB FAS Project Annual Meeting and Forum (November 8-9).  Meetings focused on specific project components were also held to discuss groundwater-surface water interactions (January 24) and groundwater processes (May 18).  Project personnel participated in multiagency meetings, including the Engineer Advisors to the Rio Grande Compact Commission (January 23, February 28), NM Federal Water Science Day (April 18), Annual Rio Grande Basin Snowmelt Runoff Forecasting meeting (April 20), and a USDA-funded UTEP project in the lower URGB (January 4, July 11).

A Middle Rio Grande Basin Study meeting (December 6) discussed possible enhancement and application of the URGB PRMS model.  Collaborative processes developed for the FAS between USGS and NM OSE in compiling water-use data are being considered to streamline future 5-year compilations.

(4) Report Products, Bibliographic Update, Data Releases, and Model Archives

The project just completed the second year of a three-year study and currently does not have any published report products, bibliographic updates, data releases, or model archives.

The following list of products will be completed in FY 2018:

Water Use Deliverables:

- USGS Scientific Investigations Report summarizing water use, water use trends and consumptive use for the URGB.

Evapotranspiration Deliverables:

- Journal article describing methods used to develop and verify monthly and seasonal ET grids at the Landsat scale using the SSEBop ET model and an analysis of results for the URGB.

Groundwater Deliverables:

- USGS Scientific Investigations Report containing hydrogeologic framework summary, structure data developed, estimated water-level surfaces and water-level change maps for selected sub-basins in the URGB, statistical analysis from the trends work, and estimates of water in storage.

- Data release of a file-based geodatabase of geospatial data.

Snow Processes Deliverables:

- SnowModel results from WY 2016 and WY 2017 summarized and provided in ScienceBase as an archived dataset.

- Journal article highlighting modeled snow variability and representivity of SNOTEL gages in URGB. Paper will include SnowModel evaluation by field surveys and National Aeronautics and Space Administration Airborne Snow Observatory (NASA ASO) and snow process sensitivity to forest change.

- Journal article on establishing linkage between SnowModel output and PRMS representation of snowmelt in the headwaters basin.

Streamflow Processes Deliverables:

- Time series estimates of baseflow discharge to streams obtained from multiple approaches at select sites in the URGB.

- Journal article describing the temporal and spatial variability in baseflow discharge to streams in the URGB.

Watershed Processes Deliverables:

- USGS Scientific Investigations Report documenting URGB PRMS model development and calibration.

- PRMS model and datasets will be provided in ScienceBase as an archived model and dataset.

- Journal article describing simulated temporal and spatial variability in water-balance components in the URGB and implications for Basin water management.

(5) PROJECT TEAM DIRECTORY

Upper Rio Grande Basin Focus Area Study

Kyle Douglas-Mankin, USGS New Mexico Water Science Center, Albuquerque NM; kdouglas-mankin@usgs.gov; 505-830-7916; Project Lead.

Water Use

Tammy Ivahnenko, USGS Colorado Water Science Center, Pueblo, CO; ivahnenk@usgs.gov; 719-562-2848; Project Component Lead: Water Use.

Natalie Houston, USGS Texas Water Science Center, Austin, TX; nhouston@usgs.gov; 512-927-3565; Water Use Specialist for TX

Amy Galanter, USGS New Mexico Water Science Center, Albuquerque, NM; agalanter@usgs.gov; 505-830-7939; Water Use Specialist for NM

Whitney Lentz, USGS Colorado Water Science Center, Pueblo, CO; wlentz@usgs.gov; 719-562-2866; Student Contractor

Amanda Rothermal, USGS Colorado Water Science Center, Pueblo CO; arothermal@usgs.gov; 719-562-2867; Student Contractor/Compiler for the CO 2015 Compilation

Diana Pedraza, USGS Texas Water Science Center, San Antonio, TX; dpedraza@usgs.gov; 210-691-9237; Geographer, Geospatial development of a semi- automated method to delineate irrigated acres in the URGB

Victoria Stengel, USGS Texas Water Science Center, Austin, TX; vstengel@usgs.gov; 512-927-3571; Geographer, Geospatial development of a semi- automated method to delineate irrigated acres in the URGB

Evapotranspiration

Gabriel Senay, USGS Earth Resource Observation and Science (EROS) Center, Fort Collins, CO; senay@usgs.gov; 605-594-2758; Project Component Lead: Evapotranspiration, geospatial ET modeling using remote sensing data.

Groundwater

Natalie Houston, USGS Texas Water Science Center, Austin, TX; nhouston@usgs.gov, 512-927-3565; Project Component Lead: Groundwater, working on all GW tasks

Jonathan Thomas, USGS Texas Water Science Center, Fort Worth, TX; jvthomas@usgs.gov, 682-316-5036; Geophysicist working on structure, cross-sections, and water level maps

Diana Pedraza, USGS Texas Water Science Center, San Antonio, TX; dpedraza@usgs.gov, 210-691-9237; Developing geodatabase containing structural basin boundaries

Toby Welborn, USGS Texas Water Science Center, Portland, OR; tlwelbor@usgs.gov, 503-251-3287; Working on water level status and trends task

Linzy Foster, USGS Texas Water Science Center, Austin, TX; lfoster@usgs.gov, 512-927-3529; Groundwater flow modeler, scheduled to work on estimating water in storage and change in storage from existing GW flow models.

Snow Processes

Graham Sexstone, USGS Colorado Water Science Center, Lakewood, CO; sexstone@usgs.gov, 303-236-6878; Project Component Lead: Snow Processes, hydrologist working on all snow tasks.

Colin Penn, USGS Colorado Water Science Center, Lakewood, CO; cpenn@usgs.gov, 303-236-6952; Hydrologist assisting with historical data compilation, GIS geodatabase development, and field work.

David Clow, USGS Colorado Water Science Center, Lakewood, CO; dwclow@usgs.gov, 303-236-6881; Research Hydrologist assisting with workplan development and manuscript preparation.

Streamflow Processes

Christine Rumsey, USGS Utah Water Science Center, Salt Lake City, UT; crumsey@usgs.gov; 801-908-5022; Project Component Lead: Streamflow Processes. Complete streamflow processes tasks, and collaborate with other project components to integrate results across the FAS.

Matt Miller, USGS Utah Water Science Center, Salt Lake City, UT; mamiller@usgs.gov; 801-908-5065; Assist with surface water processes tasks.

Watershed Processes

Kyle Douglas-Mankin, USGS New Mexico Water Science Center, Albuquerque NM; kdouglas-mankin@usgs.gov; 505-830-7916; Project Component Lead: Watershed Process.

C. David Moeser, USGS New Mexico Water Science Center, Albuquerque NM; cmoeser@usgs.gov; 801-908-5022; Watershed model development, testing, and analysis.

Study Results Visualization

Daniel Pearson, USGS Texas Water Science Center, Austin, TX; dpearson@usgs.gov, 512-927-3561; Project Component Lead: Study Results Visualization, website development and communication

Justin Hoegenauer, USGS, Texas Water Science Center, Austin, TX; jhoegenauer@usgs.gov, 512-927-3500; Website development and communication

Data Management

Diana Pedraza, USGS Texas Water Science Center, San Antonio, TX; dpedraza@usgs.gov, 210-691-9237; Project Component Lead: Data Management.

(6) PHOTOS, ANIMATIONS, AND GRAPHICS

The project website (https://txpub.usgs.gov/projects/urgb_fas/) will provide access to photos, animations, graphics, reports, maps, and other products of this study.  The website is currently live and efforts are ongoing to populate the site with current project information, results, links, and products.