Water Availability and Use Science Program

Public Supply SWUDS

FY 2016 End-of-Year Report

October 31, 2016

- PROJECT ACCOMPLISHMENTS/CONTRIBUTIONS (FY 2016)

The main objective for this work is to provide data for public-supply systems, their sources (intakes or wells) and the connections (conveyances) between the systems and sources in order to build a site-specific database in NWIS using the Site-Specific Water Use Database System (SWUDS).

Work during FY16 and FY17 concludes the funding to WSCs to develop a public supply database in SWUDS containing facility (system), water sources, conveyances, and 2010 water withdrawals. Dataset development from SDWIS-FED/PSDB was completed by Molly Maupin and Curtis Price as of FY15 and all WSCs have received SWUDS template files which they may use as the basis of this effort. During FY16, Nancy Barber developed a system with metrics to track the WSC work.  With NWULT collaboration and assistance, she contacted WSCs to determine the status of work and timeline to complete it.

Also during FY2016, Cheryl Buchwald was brought in to provide additional technical support to Nancy. She has answered questions, offering feedback, insight and support to WSCs that have specific questions or problems with coding and entering the data, and developed a plan for moving PSDB IDs from permit tables to OTID. She has begun constructing instructional tipsheets and training material that will be useful for future SWUDS database development.

Curtis Price is the data liaison to USEPA Safe Drinking Water Information System personnel in the Office of Groundwater, Drinking Water.  He made contact and requested an annual final (frozen) version of SDWIS-FED for the year 2015 in late FY16 and runs the data reconciliation scripts in MSOffice Access. This work enables a refreshed version of PSDB to be constructed with new systems and their facilities, as well as marking systems and facilities that have been combined, or discontinued to be notated.

Krissi Linsey began working with cleanup tasks in the form of a policy review of entered station names for facilities.

(2) PROJECT WORKPLAN AND BUDGET FOR FY 2017

Project Activities and timelines:

Nancy will continue to refine data completion metrics and correspondence with WSC specialists to get data entry to as near to 100% completion a possible.  It’s not possible to exactly measure data entry to PSDB because PSDB was a starting point for understanding the total population of sites and systems, and datasets used by the specialists from State agencies, which are more current, may be very different from what PSDB shows.  Because of funding limitations, it is not expected that WSCs will necessarily complete entry of all groundwater sources, although a majority of the 2010 groundwater withdrawal should be represented. Cheryl will continue to provide technical and tutorial assistance and Krissi will work on policy reviews of entered sites.

- Salary    $112,300

- Equipment/supplies (list only major items)

- Contracts (identify)

- Publications

- Travel

- Provide the total funding broken out by cost center so that the program can allocate the funding appropriately.  Spreadsheet of WSC allocations over the last 5 years is available upon request.  FY17 funding to WSCs will be wrapping up with allocation to TX, the final WSC to receive funding.

(3) NOTEWORTHY COLLABORATIONS, MEETINGS, TECHNICAL TRANSFER ACTIVITIES, SPIN-OFF PROJECT DEVELOPMENTS, AND ACKNOWLEDGEMENTS

Curtis Price, USGS, is working with Renee Morris, USEPA Office of Groundwater to obtain an updated snapshot of the EPA SDWIS-FED database for 2015. USGS will provide any improved water source locations to EPA at the end of the PS SWUDS effort.

(4) Report Products, Bibliographic Update, Data Releases, and Groundwater-Model Archives

No publications were planned for this project. Data releases would be managed by individual WSC that have entered data into NWIS with appropriate security code measures implemented.  No national data release is planned.

(5) PROJECT TEAM DIRECTORY –

Nancy Barber, NWULT Database Coordinator; SA WSC-Norcross, Georgia; 678-924-6627; nlbarber@usgs.gov; Database coordinator and liaison to NWIS and Water Use User Group (WUUG). Provides support to national team with data dissemination in reports and on the web. Lead on PS SWUDS effort.

Kristin Linsey, Support Member, New York WSC, Troy; 518-285-5636; kslinsey@usgs.gov; Krissi provides additional support to assess database updates to PS SWUDS effort.

Cheryl Buchwald, Wisconsin WSC, Madison; 608-821-3873; cabuchwa@usgs.gov; Wisconsin water-use specialist and support member for PS SWUDS coding and data entry efforts.

Curtis Price, PS SWUDS Support, South Dakota WSC, Rapid City; 605-394-3242; cprice@usgs.gov;  PS SWUDS support member and liaison to USEPA SDWIS-FED staff, and curator of master PSDB database; conducts data reconciliation in PSDB with updates from SDWIS-FED.

(6) PHOTOS, ANIMATIONS, AND GRAPHICS –