## Schedule
Study Components | FY 2016 |  |  |  | FY 2017 |  |  |  | FY 2018
| Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sept | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sept | Oct-Dec | Jan-Mar | Apr-Jun | Jul-Sept
Water Use
Refined water-use data compilation at HUC-8, AWUDS/SWUDS input
Draft water-use report in review
Population, Land-use and climate change modeling
Develop land-use change scenarios
Develop water-use and climate change scenarios
Surface-Water Modeling
Develop surface-water model (SWAT) for Cape Fear River and Pee Dee/Waccamaw River basins (2010 conditions)
Calibrate surface-water models (SWAT) to accomodate recent (200 - 2014) water-use conditions
Simulate population/land-use and climate change scenarios with SWAT models
Application of existing PRISM-2 DSS using land-use/water-use and climate change scenarios
Ecological Response Modeling
Assemble existing biological data (fish and inverts), identify study sites for space-for-time modeling, and identify sites that can be used to validate these models.
Team evaluation of biological sampling sites and review of existing response models and application to PeeDee and Cape Fear River basins
Generate ecological flow statistics from preliminary surface-water model output (Eflows package)
Develop ecological flow-response model for current (1983-2014) conditions (from SWAT models)
Run ecological flow-response model with projected changes in water-use and climate/land cover projections.
Test efficacy of ecoflow criteria and run/refine existing ecological response models and assess change under climate/population scenarios
Integrate ecological change into associated DSS/user interface
Groundwater Modeling
Data Acquisition/Compilation
Construct refined/modified groundwater flow model
Re-calibrate groundwater flow model
Develop variable-density (SEAWAT) groundwater model
Simulate groundwater management/demand and climate change scenarios
Develop groundwater decision support system(DSS)/user interface
Study Reports
Prepare, review and publish USGS Scientific Investigation Reports/Journal Articles