## WaterSMART_FY16_budget_request
EROS WaterSMART - National Water Census
Work Plan for FY16.
2015-07-22
FY16 level Funding
|  |  | A: | With level Funding as in FY15 |  | total= | 350
I | Model Application and Production |  |  |  |  | Item, $K | Group, $K
| 1 | Complete and update MODIS scale 2015 ET and stage data to the CIDA sever |  |  |  | 10 | 90
| 2 | Working closely with Molly Maupin of the NWC Water Use Team, produce 2015 CONUS-wide, |  |  |  | 30
county-based crop consumptive use estimates using MODIS-based ETa in combination
with irrigated area masks. This will require several iteration and collaboration with Molly Maupin
| 3 | For basins in the Eastern U.S., continue work to separate rainfall vs irrigation sources for ETa
|  |  | inter-clibrate energy and water balance models |  |  | 20
|  |  | Evaluate performance in consrasting hydro-climatic regions: western and eastern US |  |  | 10
| 4 | Monthly and seasonal Landsat ET for Rio Grande River basin |  |  |  | 20
Majority of required funding is expected to come from the Rio Grande Focus Area Study budget
II | Model output evaluation and opportunities
| 1 | Complete contributions to model inter-comparison work in the Upper Colorado River Basin led by Bureau of Reclamation |  |  |  | 15 | 60
| 2 | Complete contributions to model-inter-comparison work led by Utah State University; manuscript creation |  |  |  | 5
| 3 | Complete the development of a CONUS-wide ETa uncertainty map for ET |  |  |  | 15
| 4 | Work with Arizona Water Science and New Mexico Water Science centers to documenting the performance of SSEBop as compared with field methods |  |  |  | 15
| 5 | Continue to use best available data to evaluate performance of ET output in different years and locations as data becomes available |  |  |  | 10
III | Model Algorithm and Performance improvement |  |  |  |  | 10 | 130
| 1 | Iimproved data input: weather data for air temperature and potential ET |  |  |  | 15
| 2 | Cloud handling: using maksing algorithms and improved cloud detection techniques |  |  |  | 25
| 3 | Merging Landsat with MODIS to produce 8-day ET at the landsat scale, previous work was based on annual total relationships |  |  |  | 30
| 4 | Google Earth Engine ET (GEE ET):
|  |  | Complete coding of SSEBop ET model to run on earth engine platform, intial progress made |  |  | 10
|  |  | Evaluate GEE ET against desktop ET for discrepancy |  |  | 30
|  |  | Proof-of-concept CONUS-wide ET at Landsat scale for one year! |  |  | 10
IV | Synthesis and Reporting: Manuscript Development
| 1 | Manuscript preparation and publication for model-intercomparison work |  |  |  | 15 | 70
| 2 | Complete publication of Landsat 8 ET for CRB |  |  |  | 20
| 3 | Manuscript for CONUS-wide mathematically rigorous mapping of uncertainty of ETa estimates |  |  |  | 15
| 4 | Manuscript preparation for intercomparison of remote sensing ETa and ETa from field methods, with Arizona and New Mexico Water Science Centers |  |  |  | 20
|  |  |  | B: | With Additional Funding
Wish List…
Wish LIST, Additional Budget
I | Model implementation/Application |  |  |  |  | total= | 140
| 1 | Monthly and seasonal Landsat ET for Red River basin |  |  |  | 60
no fuding is expected from the Red River Basin Area Study
| 2 | Towards water availability: |  |  |  | 20
HUC-based basin water balance analysis using ET, rainfall, dischage and GRACE-based change in storage
| 3 | Historical ET with earth engine |  |  |  | 30
III | Model Algorithm and Performance improvement
|  | model paramterization: improve rate controling factrors and seasonal aggregation |  |  |  | 30