Work Plan Proposal

Water Use

By the Authors

September 16, 2011

Introduction

The DOI WaterSMART initiative – Sustain and Manage America’s Resources for Tomorrow – is working to achieve a sustainable water strategy to meet the Nation’s water needs and to ensure that this generation and generations to come will have adequate supplies of clean water to meet human and ecological needs in the face of growing competition among domestic, industrial-commercial, agricultural, and environmental uses. As part of the WaterSMART Initiative, the USGS has proposed a Water Availability and Use Assessment in the Colorado River Basin; a region where future projections of water demand along the river outpace the limited and potentially declining surface-water supply (Colorado River Basin Water Supply and Demand Study Team, 2011). The USGS has proposed a “Focus Area Study” in the Colorado River Basin to help better define the need for, and use of freshwater sources in comparison with resource availability.

In keeping with the scientific, non-regulatory mission of the USGS, water “availability” in the Colorado River Basin will be couched in terms of a water “census” evaluated by identifying the components of a regional water budget and investigating the key components of the water budget where understanding is lacking and the USGS can contribute the greatest incremental increase in the scientific understanding of these water-budget components. In consultation with Basin stakeholders the USGS has identified three water-budget topical areas where science is lacking and the USGS has particular expertise (Water Use, Hydroclimatic Variables, and Groundwater Resources). The following section discusses the proposed work plan for assessing water use in the Colorado River Basin Focus Area Study (CRBFAS)

# Problem/Background

Improved regional databases of water-use information will be one of the most essential outcomes of the National Water Census and its Geographic Focus-Area Studies. By focusing effort on water use, the U.S. Geological Survey (USGS) will be better able to characterize how humans move, utilize, consume, and dispose of the water they withdraw, divert, or impound AND to integrate that information with our understanding of natural flows in the environment. Through this integrated approach, we will hope to describe how human use of water and natural flows influence one-another. This requires that we understand the sources from which water is withdrawn (both surface-water and groundwater), the demand that the water is used to satisfy, the transport of the water to the demand location (including transportation losses), the amount of water that is “consumed” in satisfying the demand, and the volume and location of water returned to the environment, either as return flows to surface water or recharge to groundwater systems. Each of these steps has a strong geospatial component – we need to know which watersheds are losing flows, which are gaining flows, and the net exchange between watersheds.

An important aspect of developing better water-use information is the integration of water-use data from other federal, state, and regional agencies and commercial sources. These databases are essential to the success of the water-use estimation effort. In many cases, these outside entities are the primary sources of water-use data. Because States have the primary role in water-supply planning and management, they are the collectors of water-use data. State water allocation programs serve as the first source of information for many water-use sectors. Additionally, there are a number of federal water-use databases and surveys that collect information that is of great importance to water-use estimation. The US Department of Agriculture’s Census of Agriculture and Farm and Ranch Irrigation Surveys are excellent examples of this. Other federal databases include:

- US Environmental Protection Agency’s Safe Drinking Water Information System (SDWIS) for public supply withdrawals, and the National Pollution Discharge Elimination System (NPDES) and the Permit Compliance System (PCS) database that stores permitted wastewater and stormwater discharges.

- US Department of Energy – Energy Information Administration databases for water use at electric power generating plants.

- US Census Bureau’s various databases on current population enumerations and population projections (can be extrapolated to estimate rural water use).

- US Department of Agriculture, National Agriculture Statistics Service annual geospatial data layers depicting croplands and crop types (Cropland Data Layer, CDL), along with the Census of Agriculture (years ending in ‘2’ and ‘7’) and Farm and Ranch Irrigation Survey (years ending in ‘3’ and ‘8’).

Capabilities within USGS that will play critical roles in interpreting information important to CRBFAS water demand and use, and then organizing, storing and disseminating that data will include:

- Remote sensing using LANDSAT or MODIS infrared imagery for determining crop and/or riparian evapotranspiration

- Use of the National Hydrologic Dataset (NHDPlus) geospatial data layer to track the movement of water via mapped points of diversion, as well as enhancement of the hydrologic network classifications (canals/pipes over or under water features), which provide a foundation for developing the basic geospatial framework and understanding of where water is diverted, moved, used and returned on a flow-direction corrected geospatial dataset.

- Integration of water-use data into StreamStats, a web-based geospatial statistical tool that depicts stream-flow statistics and basin characteristics for ungaged user defined basins.

The CRBFAS will make use of all of these databases and tools in its water-use characterization efforts

In order to integrate water-use data with natural-flow data, the USGS will strive to improve information on the location of the points of water withdrawal, the source from which the water is withdrawn, the location of the points of demand to which the water is delivered, and the transit losses of water in route to that location. Finally, we hope that this information will allow a mass-balance estimation of the volume of the eventual “return flows” back to the environment. Due to the large area encompassed by the CRBFAS, the USGS intends to work at multiple spatial and temporal scales to develop information across the entire basin as well as demonstrate analysis and interpretative capabilities at selected sub-basin scales. The CRBFAS will compile and integrate location information in selected areas for Public Supply (“Large” and “Very Large” systems, which include population served greater than 10,000) and Irrigation water uses. Water-use information for the Industrial, Mining and Thermoelectric sectors will be compiled where available to provide as complete a summary as possible for the CRBFAS. For Public Supply, this effort will initially focus on improved information through the SDWIS database and include very large systems outside the CRBFAS only when water is transferred out of the CRBFAS to supply those systems. For Industrial water use, the PCS database will provide wastewater discharge location and returns on monthly basis for very large (major) facilities. For Irrigation, USGS will work with the USDA and the USGS National Hydrography Dataset-Plus (NHDPlus) mapping by USGS, CRBFAS States, and irrigation districts to improve the location information of diversions and crop types. Additional location data for irrigated lands also will be developed during processing of satellite imagery for estimating regional evapotranspiration as well as the USDA CDL. For Thermoelectric, good location data already exists. All location information will be tied to the NHDPlus so that the information can be accurately geospatially referenced and aggregated upstream and downstream; compilation of withdrawal data will be completed by USGS water-use program efforts. All of these efforts to locate and collect water-use data are vital to integrating those data with natural-flow information, for example using StreamStats.

Consumptive use of water is a factor that many regional stakeholders and water-supply managers have indicated as a primary focus of their management strategies, yet there is a lack of available data in this area. What data do exist are very sporadic and out of date. The Water Census will make a substantial investment in expanding our knowledge of consumptive uses for the Public Supply and Irrigation Sectors in selected watersheds in the CRBFAS. Information on consumptive uses by Thermoelectric will be supplied basin-wide by the Thermoelectric Project. The USGS intends to employ multiple methods (statistical, water balance, land cover) in the estimation of consumptive use in these selected watersheds.

Historically, USGS has published reports on significant interbasin transfers of water between watersheds at the Hydrologic Unit Code (HUC) “four-digit” scale. The last national reports on this information were conducted for water years 1972-1983 and published in the late 1980’s (Petsche, 1985; Mooty and Jeffcoat, 1986). The USGS will, as part of the CRBFAS, map and maintain a database of interbasin water transfers that are greater than 100,000 gallons per day (112 acre-ft/year), for select water-use sectors (primarily irrigation, public supply and mining) at the HUC eight-digit scale for selected watersheds during calendar year 2010. The internal-use database will contain location information on the withdrawal points and annual summaries of transfers.

Although water-use information has its own inherent value, its real power comes with the ability to integrate water-use information with natural flows in the environment to assess the influence on one to the other. This integration also would help illuminate locations where water-supply stress is the greatest and help focus informed water-management efforts. Within the Water Census it is our goal to accomplish this integration. It is our long-term objective to serve estimated water-use information, on a monthly basis if the data are available, otherwise annual or seasonal summaries will be provided along with our other hydrologic indicators. It is also our objective to serve this information so that it can be accurately located geospatially and incorporated in the water-budget analysis. Consumptive-use information for irrigation, produced as seasonal or annual estimates is achievable. The final objective is to provide estimated water-use data that can be incorporated into a water-budget analysis. This process is currently being piloted in the USGS StreamStats application.

# Benefits and Relevance

This project meets the USGS WaterSMART Focus Area goals of

1)  Gaining a greater understanding for how humans use water to meet their demands and how those demands impact ecological needs based on the natural flows and the environment, especially with respect to inter-basin transfers, and seasonal water deficits.

2)  Integrate data from various sources, both within and outside Federal entities, to a central database or data portal location whereby users can easily access information. Use existing and new methods and data to explain water-use activities, such as mapping points of diversion on national geospatial datasets, integrate remote sensing and new energy balance methods to extrapolate ET and consumptive use, and integrate the data to form as complete water budget as possible.

# Objectives

Objectives of the Water-Use Component of the WaterSMART CRBFAS are:

- to improve regional databases of water-use information for the largest types of water uses such as irrigation, public supply, mining, industrial and thermoelectric power generation, and to the extent possible as data are available, for the lesser sectors of uses of commercial, livestock and aquaculture;

- to integrate this information with our understanding of natural flows in the environment and evaluate how water resources and ecosystems are impacted by man’s manipulation of those resources. This integration requires that we understand the sources from which water is withdrawn, the demand that the water is used to satisfy, the distribution and transport mechanism of water to the demand location, the amount of water “consumed” during use or transport, and to the extent possible, the location and volume of return flows to the environment,

- to advance the use of new technologies and data to achieve the goals of data collection efforts, including the use of satellite data sets, remote sensing technologies and models, geospatial datasets and mapping tools, and web-based statistical tools; 

and

- to promote cooperation between Federal, State and local stakeholders, to create a synergistic environment for developing data delivery tools that can be easily distributed and useful to all.

# Approach and Methods

The objectives and major tasks will be accomplished using the following approaches:

- Regional database:

  - Coordinate with the USGS 2010 water-use compilation, which compiles county based annual withdrawals by source for major and minor categories of use. Reaggregate these data at the HUC-8 level.

  - Build a site-specific public-supply database (SWUDS; Site-Specific Water Use Database System. A part of USGS NWIS), and ideally populate wells and intakes, optimally with monthly withdrawals by source but may be seasonal or annual. Also include population served by system, transfers, or sales between systems. Identify withdrawal or diversion sites by HUC-8, at least. Note: some datasets will not be released to the public and may have limited availability to cooperators based on content, and USGS or USEPA security protocols.

  - Incorporate site-specific return flows (discharge) from municipal and industrial facilities to surface-water bodies to help compute consumptive use for those sectors.

- Integrate water use data with understanding of natural flows

  - Select 2-3 representative “end-member” sub-basins within the CRBFAS to demonstrate detailed water-budget aggregation and geospatial data dissemination

  - Map points of diversion on the National Hydrologic Dataset-Plus (NHDPlus) within these sub-basins for Public Supply, Irrigation, and Thermoelectric water uses.

  - Develop interactive web-based data delivery tool, based on StreamStats technology, or other proven Decision Support Systems (DSS; like SPARROW’s DSS) that will allow for analysis of user-defined estimates of water use and water budget information that are aggregated upstream from any stream point within the sub-basin.

- New technologies:

  - Use remote sensing technology to estimate evapotranspiration and consumptive use for cropland in particular, but include other vegetated lands as well.

  - Integrate water-use data with web-based enhance stream-flow statistics (e.g. StreamStats) to support site specific user-defined water-budget calculations in gaged and ungaged basins.

- Data distribution:

  - Provide raw data sets (within parameters of Homeland Security and USGS, USEPA security protocols) for download at Project data web page.

  - Develop web-based interactive basin maps to serve site specific user-defined water-budget calculations to the public.

# Task List

The primary tasks that need to be completed to accomplish the stated objectives are:

- Acquire the annual (2010) county withdrawal data for public-supply, self-supplied domestic, publicly-supplied deliveries to domestic, self-supplied industrial, irrigation, livestock, mining, aquaculture, and thermoelectric power.  Reaggregate these data for each HUC-8 sub-basin in the study area.

- At a seasonal or annual time step, characterize basin-wide uses that exist by HUC-8 basin, or site-specific if possible, otherwise county–level data will be anticipated as the base dataset. Store these data in SWUDS or AWUDS (Aggregated Water Use Database System) and build integration with a centralized data portal for the CRBFAS.

- Acquire remotely sensed measurements of evapotranspiration from the Hydroclimatic Variables component of this study and calculate consumptive use for irrigated agriculture. Apportion residual to environmental return flows in either surface water or groundwater.  Determine consumptive use for other major water use sectors (public supply and self-supplied domestic) by difference or statistical means (e.g. population served).

- Acquire thermoelectric power generation location and water-use data from Hutson team. Store withdrawals and power generation, with coefficients of use, for 2010, by site in SWUDS.

- Compile produced-water extractions and disposals from energy development (coal-bed methane) or coal extractions using coefficients or reports.

- For 2-3 selected sub-basins, map surface-water diversions, groundwater extraction sites, water transports and transfers between basins, and environmental return flows. Assign volumes and timing information to each mapped water manipulation site (anticipate seasonal timescale at best).

- Work with “data delivery” team members to incorporate water-use/consumptive use data into on-line map-based data delivery and analysis tool.

# Task Timeline:

| # Task Name | # 2011 |  |  |  | # 2012 |  |  |  | # 2013 |  |  |  | # 2014 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # 1Q | # 2Q | # 3Q | # 4Q | # 1Q | # 2Q | # 3Q | # 4Q | # 1Q | # 2Q | # 3Q | # 4Q | # 1Q | # 2Q | # 3Q | # 4Q |
| # Water-use specialists in CRB States |  |  |  |  | # x | # x | # x |  |  |  |  |  |  |  |  |  |
| # Public-supply database SWUDS |  |  |  |  | # x | # x | # x | # x | # x |  |  |  |  |  |  |  |
| # ET and Consumptive Use |  |  |  |  |  |  |  | # x | # x | # X |  |  |  |  |  |  |
| # TE and Energy water use |  |  |  |  |  | # x | # x | # X |  |  |  |  |  |  |  |  |
| # Sub-basin detailed water use |  |  |  |  |  |  |  |  |  | # x | # x | # x |  |  |  |  |
| # Mapped water use in NHDPlus(points of diversion; IR/PS/IN) |  |  |  |  |  |  |  |  |  |  | # x |  | # x |  | # X |  |
| # Irrigation withdrawals |  |  |  |  | # x | # x | # x | # x | # x |  |  |  |  |  |  |  |
| # Point of return (PCS, Mun/IN) SWUDS |  |  |  |  |  | # x | # x |  |  |  |  |  |  |  |  |  |
| # Database portal development and data upload |  |  |  |  |  |  |  | # x |  |  |  | # x |  |  |  |  |

# Deliverables

- Water-Use database compiled for entire study area and delineated at the county and HUC-8 scale. Withdrawals by source (groundwater/surface water), irrigated acres by system type, power generation, population served by public-supply and self-supply domestic population.

- Tabulated consumptive-use estimates for public-supply, self-supplied domestic, irrigated agriculture, and thermoelectric power uses.

- Detailed water-use information for 2-3 sub-basin areas to be utilized in web-based data-delivery demonstration exercise.

- Fact sheet outlining water-use activities in CRBFAS; end of FY12

- SIR water-use report summarizing water-use, consumptive use, and interbasin transfers for 2010; end of FY14.

# Personnel Requirements

| Project | Tasks | FY12 | FY13 | FY14 |
| --- | --- | --- | --- | --- |
| Project Chief | Planning, coordination, data interpretation, report preparation | 20 weeks | 13 weeks | 6 weeks |
| Hydrologist | 2.25 FTE split between 6 WSC wu specialists or capable hydrologist/hydrologic technician. Compile 2010 compilation data, assist in other tasks (CU/POD) as assigned. | 156 weeks | 80 weeks | 6 weeks |

Report Costs:		Fact Sheet		$5,000

SIR			$10,000 (printed copies)

# Project Budget

## Funding

|  | FY12 | FY13 | FY14 | Total |
| --- | --- | --- | --- | --- |
| USGS | $366,800 | $195,000 | $50,000 | $611,800 |

References:

Colorado River Basin Water Supply and Demand Study Team, 2011, Colorado River Basin water supply and demand study: Bureau of Reclamation Interim Report No. 1, 69 p.