Project Title: Regional Groundwater Availability and Use Studies – WAUSP Function

Project Chief:  Various Project Chiefs for the portfolio of studies, managed by the WAUSP leadership team

Project Summary:

What are you trying to do? Articulate your objectives using absolutely no jargon.

- Assess Regional Groundwater Availability for the Principal Aquifers of the nation:

  - document the effects of human activities on water levels, groundwater storage, and discharge to streams and other surface-water bodies;

  - explore climate variability impacts on the regional groundwater system; and

  - demonstrate analysis to evaluate the adequacy of data networks to understand groundwater availability at a regional scale.

How is it done today, and what are the limits of current practice?

- Regional studies are done by USGS primarily using existing data, usually through application of MODFLOW

- Limits: data sources are varied and may be lacking; data compilation becomes major task

What's new in your approach and why do you think it will be successful?

- Individual Regional Groundwater Availability studies have developed or implemented  new features in MODFLOW to perform the regional analysis

- Individual studies also have looked at innovative ways to combine a variety of data sources to make a GW availability story

Who cares? If you're successful, what difference will it make? What are the risks and the payoffs?

- National synthesis of groundwater availability sought by Congress (Circular 1323, Circular 1384)

- Risk: regional studies can be difficult for local stakeholders to appreciate.

- Payoff: regional studies provide platform for local analysis and decision making.

How much will it cost? How long will it take? What are the midterm and final "exams" to check for success?

- Each study costs 1.2 – 1.5 million over 3-4 years

- 30 Principal aquifer: 25-30 studies – represent 94 percent of total groundwater withdrawals

Regional Groundwater Availability Studies

Statement of Project Goals

Regional groundwater availability studies are a significant part of the Water Availability and Use Science Program (https://water.usgs.gov/ogw/gwrp/activities/gw-avail.html). These studies are designed to develop a national assessment of groundwater availability in USGS Principal Aquifers as part of a National Water Census.

The studies seek to quantify:

- the status of groundwater resources,

- how these resources have changed over time, and

- likely system response to future changes in anthropogenic and environmental conditions.

The studies also provide a platform for methods development and application.  Notable methods development activities include the use of TSPROC and other PEST tools to aid in model calibration, application of SWB for recharge estimation, and application of Unstructured-Grid MODFLOW.  Current projects are using advanced uncertainty analysis and fit-for-purpose modeling concepts to more fully integrate the model calibration and prediction activities and are planning to develop and use features in MODFLOW-6.

Background

The portfolio of projects included as Regional Groundwater Availability Studies pre-date the National Water Census as the effort to access groundwater availability in the United States as described in Circulars 1223 and 1323 (U.S. Geological Survey, 2002; Reilly and others, 2008) and the broader Water Census described in Circular 1384 (Alley and others, 2013) build on a group of studies started in 2004. However, evaluation of groundwater resources has a much longer history within USGS. Reports to Congress in this area include Meinzer (1923) and McGuiness (1950s and 1960s) and continue through the Regional Aquifer System Analysis (RASA) Program 1980s and 1990s (Sun and Johnson, 1994). The Middle Rio Grande project falls between the RASA Program and the initiation of the regional groundwater availability studies in 2004.  Appendix A provides a bibliography from the regional groundwater availability studies funded directly through the Groundwater Resources and Water Availability and Use Science Programs. Two of the projects were part of a National Water Availability and Use Pilot which eventually were used to support the development of the National Water Census.

Objectives

The objectives of Regional Groundwater Availability studies focus on groundwater quantity and the response of the groundwater system to changes from development or external conditions including climate.  Three components of the individual studies are to quantify the status of groundwater resources, analyze how these resources have changed over time to build understanding of the system, and predict likely system response to future changes in anthropogenic and environmental conditions. Typically the studies do not include new data collection, rather they extensively rely on existing data and often the compilation of data from various local, regional, and national sources into a consistent framework is a major contribution of a study.  These three components: quantify, understand, and predict are consistent with the USGS Water Science Strategy (Evenson and others, 2013) and provide a foundation for individual studies to be adapted to the specific conditions for the aquifer system under consideration and the stresses applied to that system.

Scope

The spatial scope of the portfolio of studies is nationwide and is based on the principal aquifers (U.S. Geological Survey, 2003). The thirty principal aquifers that have the highest groundwater withdrawals provide approximately 94 percent of the groundwater used for public supply, irrigation, and self-supplied industrial uses (Reilly and others, 2008).

Figure 1. Principal aquifers of the United States.

Figure 2. Principal aquifers that provided the most total withdrawals for irrigation, public-supply, and self-supplied industrial water in the United States in 2000 (from Reilly and others, 2008 and Maupin and Barber, 2005).

Approach

Most regional groundwater availability studies provide the quantification of the status, analysis of the effects of development, and predictive tools for the principal aquifer through application of MODFLOW modeling at a regional scale. Some principal aquifers, however, are collections of many local aquifers sharing common characteristics and development of a single numerical model for these systems may not be appropriate.  For these systems, the groundwater conditions are quantified using existing data, analysis of baseflow conditions, and often estimation of recharge and water use.

The Water Availability and Use Science Program adopted the approach from the Groundwater Resources Program for selection of new principal aquifer projects.  Brief pre-proposals were solicited from water science centers and ranked by a review team from the technical offices, water science field team, and program leads from related programs.  Several finalists were selected as funded to write complete workplans that were again reviewed by the review team.  For FY17 one project was selected for a full workplan and two were selected to receive limited funding in a phased approach for proof-of-concept testing of the proposed work.  Two workplans were held for future funding in FY18 or FY19.  We anticipate that a similar procedure will be used within the revised Water Mission Area structure with proposals solicited by the WAUSP and work coordinated by the appropriate divisions in Mission Delivery.

Relation to other USGS Regional and National Programs, Projects and Mission Areas

The regional groundwater availability projects often provide a base regional model for  analysis within the NAWQA project cycle III groundwater studies.  These projects include the Central Valley, Northern Atlantic Coastal Plain, and Mississippi Embayment studies.  The glacial principal aquifer studies under WAUSP and the NAWQA project were conducted at the same time and the two teams worked on coordinating efforts, sharing base data, and several staff were funded by both projects helping them to focus on regional questions and facilitating information transfer between the project teams.

Relation to local USGS projects, stakeholder needs, and collaborative opportunities

Regional groundwater availability projects have provided significant potential for spin-off and follow-on work by local, state, and regional cooperators.  Notably, the Central Valley and Mississippi Embayment groundwater-flow models and the data assembled for use in these models have been extensively used by state and local cooperators leading to significant funding for USGS water science centers.

Current Projects, FY17 Budget Request, and Expected End Date

| Project | Task Number | FY17 Request | End Date | Comment |
| --- | --- | --- | --- | --- |
| Regional Study Support | 400 | 140,000 | Year-to-year | Also 77,063 in Fy16 carryover |
| Floridan | 402 | 394,620 | FY18 |  |
| Glacial | 403 | 60,000 | FY17 |  |
| Hawaii Volcanics | 404 | 270,100 | FY18 |  |
| Ozarks | 405 | 325,000 | FY18 |  |
| NW Volcanics | 406 | 117,000 | Phase 1, FY17 | Phase 1 wrap up, phase 2 proposed |
| Brackish | 407 | 164,500 | Complete, May 2017 |  |
| High Plains | 408 | 64,200 | FY17 |  |
| Williston-Powder River | 411 | 138,000 | FY17 |  |
| TAAP | 412 | 1,000,000 | FY20 | 500,000 to WRIR |
| MAP | 413 | 1,000,000 | FY21 | + airborne geophysics? |
| Coastal Lowlands | 414 | 456,743 | FY21 |  |
| California Coastal Basin | 415 | 211,535 | Mid FY18 for phase 1 | Phase 1 |
| Colorado Plateau | 417 | 127,000 | Mid FY18 for phase 1 | Phase 1 |
| Appalachian Plateaus |  | 0 | FY17 |  |

References

Alley, W.M., Evenson, E.J., Barber, N.L., Bruce, B.W., Dennehy, K.F., Freeman, M.C., Freeman, W.O., Fischer, J.M., Hughes, W.B., Kennen, J.G., Kiang, J.E., Maloney, K.O., Musgrove, MaryLynn, Ralston, Barbara, Tessler, Steven, and Verdin J.P., 2013, Progress toward establishing a national assessment of water availability and use: U.S. Geological Survey Circular 1384, 34 p., available at https://pubs.usgs.gov/circ/1384.

Evenson, E.J., Orndorff, R.C., Blome, C.D., Böhlke, J.K., Hershberger, P.K., Langenheim, V.E., McCabe, G.J., Morlock, S.E., Reeves, H.W., Verdin, J.P., Weyers, H.S., and Wood, T.M., 2013, U.S. Geological Survey water science strategy—Observing, understanding, predicting, and delivering water science to the Nation: U.S. Geological Survey Circular 1383–G, 49 p., also available at https://pubs.usgs.gov/circ/1383g/.

Maupin, M.A., and Barber, N.L., 2005, Estimated withdrawals from principal aquifers in the United States, 2000: U.S. Geological Survey Circular 1279, 46 p.

McGuinness, C.L., 1951, The water situation in the United States with special reference to ground water— with a summary of the current water situation by states based on data supplied by field offices of the Water Resources Division: U.S. Geological Survey Circular 114, 127 p., accessed November 29, 2013, at http://pubs.er.usgs.gov/publication/cir114.

McGuinness, C.L., 1963, The role of ground water in the national water situation— with state summaries based on reports by district offices of the Ground Water Branch: U.S. Geological Survey Water-Supply Paper 1800, 1121 p., 4 plates, accessed November 29, 2013, at http://pubs.er.usgs.gov/publication/wsp1800.

Meinzer, O.E., 1923, The occurence of ground water in the United States with a discussion of principles: U.S. Geological Survey Water-Supply Paper 489, 321 p., 23 plates, accessed November 29, 2013, at http://pubs.er.usgs.gov/publication/wsp489.

Reilly, T.E., Dennehy, K.F., Alley, W.M., and Cunningham, W.L., 2008, Ground-Water Availability in the United States:  U.S. Geological Survey Circular 1323, 70 p., also available online at http://pubs.usgs.gov/circ/1323/.

Sun, R.J, and Johnson, R.H., 1994, Regional Aquifer-System Analysis Program of the U.S. Geological Survey, 1978-1992:  U.S. Geological Survey Circular 1099, 126 p., also available at https://pubs.er.usgs.gov/publication/cir1099/.

U.S. Geological Survey, 2002, Concepts for national assessment of water availability and use: U.S. Geological Survey Circular 1223, 34 p., also availabile online at https://pubs.er.usgs.gov/publication/cir1223.

U.S. Geological Survey, 2003, Principal aquifers of the 48 conterminous United States, Hawaii, Puerto Rico, and the U.S. Virgin Islands: U.S. Geological Survey, accessed May 10, 2017, at https://water.usgs.gov/ogw/aquifer/map.html.

Appendix A – Bibliography

Water Availability and Use Pilot Studies:

Great Lakes Basin Pilot

Arihood, L.D., 2009, Processing, analysis, and general evaluation of well-driller records for estimating hydrogeologic parameters of the glacial sediments in a ground-water flow model of the Lake Michigan Basin: Scientific Investigations Report 2008-5184, 26 p. (http://pubs.usgs.gov/sir/2008/5184/)

Buchwald, C.A., Luukkonen, C.L., and Rachol, C.M., 2010, Estimation of groundwater use for a groundwater-flow model of the Lake Michigan Basin and adjacent areas, 1864-2005:  U.S. Geological Survey Scientific Investigations Report 2010-5068, 120 p. (http://pubs.usgs.gov/sir/2010/5068/)

Coon, W.F., and Sheets, R.A., 2006, Estimate of ground water in storage in the Great Lakes Basin, United States, 2006: U.S. Geological Survey Scientific Investigations Reports 06-5180, 19 p. (http://pubs.usgs.gov/sir/2006/5180/)

Feinstein, D.T., Hunt, R.J., and Reeves, H.W., 2010, Regional groundwater-flow model of the Lake Michigan Basin in support of Great Lakes Basin Water Availability and Use Studies: U.S. Geological Survey Scientific Investigations Report 2010-5109, 379 p. (http://pubs.usgs.gov/sir/2010/5109/)

Fienen, M.N., Doherty, J.E., Hunt, R.J., and Reeves, H.W., 2010, Using prediction uncertainty analysis to design hydrologic monitoring networks: Example applications from the Great Lakes water availability pilot project: U.S. Geological Survey Scientific Investigations Report 2010–5159, 44 p. (http://pubs.usgs.gov/sir/2010/5159/)

Grannemann, N.G. and Reeves, H.W., 2005, Great Lakes Basin Water Availability and Use – A study of the National Water Availability and Water Use Program: U.S. Geological Survey Fact Sheet 2005-3113, 4 p. (http://pubs.usgs.gov/fs/2005/3113/pdf/FS2005_3113.pdf)

Haitjema, H.M., Feinstein, D.T, Hunt, R.J. and Gusyev, M.A., 2010, A hybrid finite-difference and analytic element groundwater model: Ground Water, v. 48, no. 4, 538-548.

Hoard, C.J., 2010, Implementation of local grid refinement (LGR) for the Lake Michigan Basin Regional groundwater-flow model:  U.S. Geological Survey Scientific Investigations Report 2010-5117, 25 p. (http://pubs.usgs.gov/sir/2010/5117/)

Hodgkins, G.A., Dudley, R.W., and Aichele, S.S., 2007, Historical changes in precipitation and streamflow in the U.S. Great Lakes Basin, 1915-2004: U.S. Geological Survey Scientific Investigations Report 2007-5118, 31 p. (http://pubs.usgs.gov/sir/2007/5118)

Holtschlag, D.J., 2010, Application guide for AFINCH (analysis of flows in networks of channels) described by NHDplus:  U.S. Geological Survey Scientific Investigations Report 2009-5188, 106 p. (http://pubs.usgs.gov/sir/2009/5188/)

Koltun, G.F., and Holtschlag, D.J., 2010, Application of AFINCH as a tool for evaluating the effects of streamflow-gaging-network size and composition on the accuracy and precision of streamflow estimates at ungaged locations in the Southeast Lake Michigan Hydrologic Subregion: U.S. Geological Survey Scientific Investigations Report 2010–5020, 14 p. (http://pubs.usgs.gov/sir/2010/5020/)

Lampe, D.C., 2009, Hydrogeologic framework of bedrock units and initial salinity distribution for a simulation of groundwater flow for the Lake Michigan Basin: U.S. Geological Survey Scientific Investigations Report 2009–5060, 49 p. (http://pubs.usgs.gov/sir/2009/5060/)

Mills, P.C., and Sharpe, J.B., 2010, Estimated withdrawals and other elements of water use in the Great Lakes Basin of the United States in 2005: U.S. Geological Survey Scientific Investigations Report 2010–5031, 95 p. (http://pubs.usgs.gov/sir/2010/5031/)

Neff, B.P., Piggott, A.R., and Sheets, R.A., 2006, Estimation of shallow ground-water recharge in the Great Lakes basin: U.S. Geological Survey Scientific Investigations Report 2005-5284, 31 p. (http://pubs.usgs.gov/sir/2005/5284/)

Reeves, H.W., 2010, Water Availability and Use Pilot— Multi-Scale Assessment in the U.S. Great Lakes Basin:  U.S. Geological Survey Professional Paper 1778, 105. (http://pubs.usgs.gov/pp/1778/)

Shaffer, K.H., and Runkle, D.L., 2007, Consumptive water-use coefficients for the Great Lakes Basin and climatically similar areas: U.S. Geological Survey Scientific Investigations Report 2007-5197, 191 p. (http://pubs.usgs.gov/sir/2007/5197/)

Shaffer, K.H., 2008, Consumptive water use in the Great Lakes Basin: U.S. Geological Survey Fact Sheet 2008–3032, 6 p. (http://pubs.usgs.gov/fs/2008/3032/pdf/fs2008-3032.pdf)

Shaffer, K.H., 2009, Variations in withdrawal, return flow, and consumptive use of water in Ohio and Indiana, with selected data from Wisconsin, 1999–2004: U.S. Geological Survey Scientific Investigations Report 2009–5096, 93 p. (http://pubs.usgs.gov/sir/2009/5096/)

Sheets, R.A., and Simonson, L.A., 2006, Compilation of regional ground-water divides for principal aquifers corresponding to the Great Lakes basin, United States: U.S. Geological Survey Scientific Investigations Report 2006-5102, 23 p. (http://pubs.usgs.gov/sir/2006/5102/)

Westenbroek, S.M., Kelson, V.A., Dripps, W.R., Hunt, R.J., and Bradbury,K.R., 2010, SWB—A modified Thornthwaite-Mather Soil-Water-Balance code for estimating groundwater recharge: U.S. Geological Survey Techniques and Methods 6–A31, 60 p. (http://pubs.usgs.gov/tm/tm6-a31/) [partially funded by Great Lakes Basin Pilot]

Wilcox, D.A., Thompson, T.A., Booth, R.K., and Nicholas, J.R., 2007, Lake-level variability and water availability in the Great Lakes:  U.S. Geological Survey Circular 1311, 25 p. (http://pubs.usgs.gov/circ/2007/1311/)

Southwest Alluvial Basins Project – Groundwater methods development

Tillman, Fred D, Leake, Stanley A., Flynn, Marilyn E., Cordova, Jeffrey T., and Schonauer, Kurt T., 2007, An online interactive map service for displaying ground-water conditions in Arizona:  U.S. Geological Survey Open-File Report 2007-1436, 16 p.[http://pubs.usgs.gov/of/2007/1436/].

Tillman, Fred D., Leake, Stanley A., Flynn, Marilyn E., Cordova, Jeffrey T., Schonauer, Kurt T., and Dickinson, Jesse E., 2008, Methods and indicators for assessment of regional ground-water conditions in the southwestern United States:  U.S. Geological Survey Scientific Investigations Report 2008-5209,  22 p. [http://pubs.usgs.gov/sir/2008/5209/].

Tillman, Fred D, 2009, Excel(R) spreadsheet tools for analyzing groundwater level records and displaying information in ArcMap(TM): U.S. Geological Survey Techniques and Methods 4-F1, 59 p. [http://pubs.usgs.gov/tm/tm4f1/].

Regional Groundwater Availability Studies

Middle Rio Grande (1995-2001)

Bartolino, J.R., and Cole, J.C., 2002, Ground-water resources of the Middle Rio Grande Basin, New Mexico: U.S. Geological Survey Circular 1222, 132 p.

Plummer, L. Niel, Bexfield, Laura M., Anderholm, Scott K., Sanford, Ward E., and Busenberg, Eurybiades, 2004, Geochemical characterization of ground-water flow in the Santa Fe Group aquifer system, Middle Rio Grande Basin, New Mexico. U.S. Geological Survey Water-Resources Investigations Report 03-4131 395p.

Plummer, L.N., W.E. Sanford, L.M. Bexfield, S.K. Anderholm, and E. Busenberg, 2004, Using geochemical data and aquifer simulation to characterize recharge and groundwater flow in the Middle Rio Grande Basin, New Mexico, in Groundwater Recharge in a Desert Environment: The Southwestern United States, edited by J.F. Hogan, F.M. Phillips, and B.R. Scanlon, Water Science and Applications Series, vol. 9, American Geophysical Union, Washington, D.C., 185-216.

Sanford, W.E., Plummer, L.N., McAda, D.P., Bexfield, L.M., and Anderholm, S.K., 2004, Use of environmental tracers to estimate parameters for a predevelopment-ground-water-flow model of the Middle Rio Grande Basin, New Mexico: U. S. Geological Survey Water-Resources Investigations Report 03-4286, 102 p.

Sanford Ward E., Plummer L. Niel, McAda, Douglas P., Bexfield, Laura M., Anderholm, Scott K., 2004, Hydrochemical tracers in the Middle Rio Grande Basin, USA: 2. Calibration of a groundwater model. Hydrogeology Journal, v. 12, p. 389-407.

Bexfield, L. M., and Plummer, L. N., 2003, Occurrence of arsenic in ground water of the Middle Rio Grande Basin, central New Mexico, in Welch, A. H., and Stollenwerk, K. G., eds., Arsenic in Ground Water: Geochemistry and Occurrence, Kluwer Academic Publishers, Chapter 11, p. 295-327.

Plummer, L. Niel, Bexfield, Laura, M., Anderholm, Scott K., Sanford, Ward E., and Busenberg, Eurybiades, 2003, Hydrochemical tracers in the Middle Rio Grande Basin, USA: 1. Conceptualization of groundwater flow. Hydrogeology Journal, v. 12, p. 359-388.

Bartolino, J.R., Cole, J.C., and Hester, D.J., 2002, Ground-Water Resources of the Middle Rio Grande Basin: U.S. Geological Survey Fact Sheet FS-088-02, 6 pages.

Denver Basin

Paschke, S.S. ed., 2011, Groundwater availability of the Denver Basin aquifer system, Colorado: U.S. Geological Survey Professional Paper 1770, 274 p.

Chapter A: Introduction, Conceptual Model, Hydrogeologic Framework, and Predevelopment Groundwater Availability of the Denver Basin Aquifer System, Colorado, By Suzanne S. Paschke, Edward R. Banta, Jean A. Dupree, and Joseph P. Capesius

Chapter B: Effects of Development on Groundwater Availability in the Denver Basin Aquifer System, Colorado, By Suzanne S. Paschke, Edward R. Banta, and David W. Litke

Chapter C: Groundwater Flow Simulations of the Denver Basin Aquifer System, Colorado, By Edward R. Banta, Suzanne S. Paschke, and David W. Litke

North and South Carolina Atlantic Coastal Plain Aquifer System

Campbell, B.G., and Coes, A.L., eds., 2010, Groundwater availability in the Atlantic Coastal Plain of North and South Carolina: U.S. Geological Survey Professional Paper 1773, 241 p., 7 pls., available online at http://pubs.usgs.gov/pp/1773/

Chapter A: Groundwater Availability in the Atlantic Coastal Plain of North and South Carolina, By Bruce G. Campbell, Jason M. Fine, Matthew D. Petkewich, Alissa L. Coes, and Silvia Terziotti

Chapter B: Hydrogeologic Framework of the Atlantic Coastal Plain, North and South Carolina, By Joseph A. Gellici and Jeff C. Lautier

Chapter C: Simulation of Groundwater Flow in the Atlantic Coastal Plain, North and South Carolina and Parts of Eastern Georgia and Southern Virginia, Predevelopment to 2004, By Alissa L. Coes, Bruce G. Campbell, Matthew D. Petkewich, and Jason M. Fine

Harrelson, L.G., and Fine, J.M., 2006, Selected well data used in determining ground-water availability in the North and South Carolina Atlantic Coastal Plain aquifer systems: U.S. Geological Survey Open-File Report 2006–1298, 81 p., available online at http://pubs.water.usgs.gov/ofr2006-1298/

Central Valley of California

Faunt, C.C. ed., 2009, Groundwater Availability of the Central Valley Aquifer: U.S. Geological Survey Professional Paper 1766, 225 p. Available at http://pubs.usgs.gov/pp/1766/

Chapter A: Introduction, Overview of Hydrogeology, and Textural Model of California’s Central Valley. By Claudia C. Faunt, Randall T. Hanson, and Kenneth Belitz

Chapter B: Groundwater Availability in California’s Central Valley. By Claudia C. Faunt, Kenneth Belitz, and Randall T. Hanson

Chapter C: Numerical Model of the Hydrologic Landscape and Groundwater Flow in California’s Central Valley. By Claudia C. Faunt, Randall T. Hanson, Kenneth Belitz, Wolfgang Schmid, Steven P. Predmore, Diane L. Rewis, and Kelly McPherson

Appendix 1: Supplemental Information—Modifications to Modflow-2000 Packages and Processes. By Wolfgang Schmid and R.T. Hanson

Faunt, C.C., Hanson, R.T., Belitz, Kenneth, and Rogers, Laurel, 2009, California’s Central Valley Groundwater Study— A powerful new tool to assess water resources in California’s Central Valley: U.S. Geological Survey Fact Sheet 2009-3057, 4 p.

Faunt, C.C., Belitz, K., and Hanson, R.T., 2009, Development of a three-dimensional model of sedimentary texture in valley-fill deposits of Central Valley, CA, USA, Hydrogeology Journal v. 18, p. 625-649. DOI 10.1007/s10040-009-0539-7 http://ca.water.usgs.gov/projects/central-valley/HydrogeologyJournal-2010-18.pdf

Scanlon, Bridget; Reedy, Robert; Faunt, Claudia; Pool, Donald; Uhlman, Kristine, 2016, Enhancing drought resilience with conjunctive use and managed aquifer recharge in California and Arizona,  Environmental Research Letters, 2016; 11 (3): 035013 DOI: 10.1088/1748-9326/11/3/035013

Faunt, Claudia C., Sneed, Michelle, Traum, Jonathan A., and Brandt, Justin, 2016, Water availability and land subsidence in the Central Valley, California, USA, Hydrogeology Journal Hydrogeology Journal: Vol. 24, No. 3, p. 675-684. DOI: 10.1007/s10040-015-1339-x

Faunt, Claudia C., and Sneed, Michelle, 2015, Water Availability and Subsidence in California's Central Valley, Essay in San Francisco Estuary and Watershed Science: 13 (3), http://escholarship.org/uc/item/6qn2711x

Scanlon, B.R., Faunt, C.C., Longuevergne, L., Reedy, R.C., Alley, W.M., McGuire, V.L. and McMahon, P.B., 2012, Groundwater Depletion and Sustainability of Irrigation in the US High Plains and Central Valley. Proceedings of the National Academy of Sciences, 109, 9320-9325. http://dx.doi.org/10.1073/pnas.1200311109

Hanson, R.T., Flint, L.E., Flint, A.L., Dettinger, M.D., Faunt, C.C., Cayan, D., and Schmid, W., 2012, A method for physically based model analysis of conjunctive use in response to potential climate changes, Water Resources Research, vol. 48, W00L08, doi:10.1029/2011WR010774

Hanson, R.T., Flint, A.L., Flint, L.E. Faunt, C.C, Schmid, W. Dettinger, M.D., Leake, S.A., and Cayan, D.R., 2010, Integrated simulation of consumptive use and land subsidence in the Central Valley, California, for the past and for a future subject to urbanization and climate change, Land Subsidence, Associated Hazards and the Role of Natural Resources Development (Proceedings of EISOLS 2010, Querétaro, Mexico, 17–22 October 2010). IAHS Publ. 339, 2010.

Great Basin Carbonate and Alluvial Aquifer System

Heilweil, V.M., and Brooks, L.E., eds., 2011, Conceptual model of the Great Basin carbonate and alluvial aquifer system: U.S. Geological Survey Scientific Investigations Report 2010-5193, 191 p.

Chapter A: Introduction, By Victor M. Heilweil, Donald S. Sweetkind, and David D. Susong

Chapter B: Hydrogeologic Framework, By Donald S. Sweetkind, Jay R. Cederberg, Melissa D. Masbruch, and Susan G. Buto

Chapter C: Groundwater Flow, By Donald S. Sweetkind, Melissa D. Masbruch, Victor M. Heilweil, and Susan G. Buto

Chapter D: Estimated Groundwater Budget, By Melissa D. Masbruch, Victor M. Heilweil, Susan G. Buto, Lynette E. Brooks, David D. Susong, Alan L. Flint, Lorraine E. Flint, and Philip M. Gardner

Appendix 1: Three-Dimensional Hydrogeologic Framework, By Jay R. Cederberg, Donald S. Sweetkind, Susan G. Buto, and Melissa D. Masbruch

Appendix 2: Descriptive Information for Each Hydrographic Area within the Great Basin Carbonate and Alluvial Aquifer System Study Area, By Victor M. Heilweil and Susan G. Buto

Appendix 3: Input, Calibration, Uncertainty, and Limitations of the Basin Characterization Model, By Alan L. Flint, Lorraine E. Flint, and Melissa D. Masbruch

Appendix 4: Current Study Groundwater Recharge Estimates for Predevelopment Conditions and Ranges of Previously Reported Estimates of Groundwater Recharge for Each Hydrographic Area within the Great Basin Carbonate and Alluvial Aquifer System Study Area, By Melissa D. Masbruch

Appendix 5: Current Study Groundwater Discharge Estimates for Predevelopment Conditions and Ranges of Previously Reported Estimates of Groundwater Discharge for Each Hydrographic Area within the Great Basin Carbonate and Alluvial Aquifer System Study Area, By Melissa D. Masbruch

Appendix 6: Description of Spatial Datasets Accompanying the Conceptual Model of the Great Basin Carbonate and Alluvial Aquifer System, By Susan G. Buto

Appendix 7: Predevelopment and Recent (2000) Groundwater Budget Estimates for Each Hydrographic Area within the Great Basin Carbonate and Alluvial Aquifer System Study Area, By Melissa D. Masbruch

Appendix 8: Development of Historical Well Withdrawal Estimates for the Great Basin Carbonate and Alluvial Aquifer System Study Area, 1940–2006, By Melissa D. Masbruch and Victor M. Heilweil

Mississippi Embayment Regional Aquifer System

Clark, B.R., and Freiwald, D.A., 2011, A new tool to assess groundwater resources in the Mississippi embayment: U.S. Geological Survey Fact Sheet 2011–3115, 4 p.

Clark, B.R., Hart, R.M., and Gurdak, J.J., 2011, Groundwater availability of the Mississippi embayment: U.S. Geological Survey Professional Paper 1785, 62 p.

Clark, B.R., and Hart, R.M., 2009, The Mississippi Embayment Regional Aquifer Study (MERAS): Documentation of a groundwater-flow model constructed to assess water availability in the Mississippi Embayment: U.S. Geological Survey Scientific Investigations Report 2009-5172, 61 p.

Hart, R.M., and Clark, B.R., 2008, Geophysical log database for the Mississippi Embayment Regional Aquifer Study (MERAS): U.S. Geological Survey Scientific Investigations Report 2008-5192, 8 p.

Hart, R.M., Clark, B.R., and Bolyard, S.E., 2008, Digital surfaces and thicknesses of selected hydrogeologic units within the Mississippi Embayment Regional Aquifer Study (MERAS): U.S. Geological Survey Scientific Investigations Report 2008-5098, 33 p.

Schrader, T.P., 2007, Potentiometric surface in the Sparta-Memphis aquifer of the Mississippi Embayment, spring 2007: U.S. Geological Survey Scientific Investigations Map 3014, 1 sheet.

Columbia Plateau Regional Aquifer System

Burns, E.R, Snyder, D.T, Haynes, J.V., and Waibel, M.S., 2012, Groundwater status and trends for the Columbia Plateau Regional Aquifer System, Washington, Oregon, and Idaho: U.S. Geological Survey Scientific Investigations Report 2012–5261, 52 p., http://pubs.er.usgs.gov/publication/sir20125261.

Burns, E.R., Morgan, D.S., Peavler, R.S., and Kahle, S.C., 2011, Three-dimensional model of the geologic framework for the Columbia Plateau Regional Aquifer System, Idaho, Oregon, and Washington: U.S. Geological Survey Scientific Investigations Report 2010-5246, 44 p.

Ely, D.M., Burns, E.R., Morgan, D.S., and Vaccaro, J.J., 2014, Numerical simulation of groundwater flow in the Columbia Plateau Regional Aquifer System, Idaho, Oregon, and Washington: U.S. Geological Survey Scientific Investigations Report 2014–5127, 90 p., http://dx.doi.org/10.3133/sir20145127.

J.J. Vaccaro, S.C. Kahle, D.M. Ely, E.R. Burns, D.T. Snyder, J.V. Haynes, T.D. Olsen, W.B. Welch, and D.S. Morgan, 2015, Groundwater availability of the Columbia Plateau Regional Aquifer System, Washington, Oregon, and Idaho: U.S. Geological Survey Professional Paper 1817, 87 p., http://dx.doi.org/10.3133/pp1817.

Kahle, S.C., Morgan, D.S., Welch, W.B., Ely, D.M., Hinkle, S.R., Vaccaro, J.J., and Orzol, L.L., 2011, Hydrogeologic framework and hydrologic budget components of the Columbia Plateau Regional Aquifer System, Washington, Oregon, and Idaho: U.S. Geological Survey Scientific Investigations Report 2011–5124, 66 p.

Kahle, S.C., Olsen, T.D., and Morgan, D.S., 2009, Geologic setting and hydrogeologic units of the Columbia Plateau Regional Aquifer System, Washington, Oregon, and Idaho: U.S. Geological Survey Scientific Investigations Map 3088, 1 sheet.

Snyder, D.T., and Haynes, J.V., 2010, Groundwater conditions during 2009 and changes in groundwater levels from 1984 to 2009, Columbia Plateau Regional Aquifer System, Washington, Oregon, and Idaho: U.S. Geological Survey Scientific Investigations Report 2010-5040, 12 p.

Sue C. Kahle and John J. Vaccaro, 2015, Groundwater resources of the Columbia Plateau regional aquifer system: U.S. Geological Survey Fact Sheet 2015-3063, 6 p., http://dx.doi.org/10.3133/fs20153063.

U.S. Geological Survey, 2008, Ground-Water Availability Assessment for the Columbia Plateau Regional Aquifer System, Washington, Oregon, and Idaho: U.S. Geological Survey Fact Sheet FS-2008-3086, 2 p.

High Plains Aquifers

Houston, N.A., Gonzales-Bradford, S.L., Flynn, A.T., Qi, S.L., Peterson, S.M., Stanton, J.S., Ryter, D.W., Sohl, T.L., and Senay, G.B., 2013, Geodatabase compilation of hydrogeologic, remote sensing, and water-budget-component data for the High Plains aquifer, 2011: U.S. Geological Survey Data Series 777, 12 p.

Qi, S.L., 2010, Digital Map of Aquifer Boundary for the High Plains Aquifer in Parts of Colorado, Kansas, Nebraska, New Mexico, Oklahoma, South Dakota, Texas, and Wyoming: U.S. Geological Survey Data Series 543.

Qi, Sharon L., Christenson, Scott, 2010, Assessing Groundwater Availability in the High Plains Aquifer in Parts of Colorado, Kansas, Nebraska, New Mexico, Oklahoma, South Dakota, Texas, and Wyoming: U.S. Geological Survey Fact Sheet FS-2010-3008, 4 p.

Stanton, J.S., Qi, S.L., Ryter, D.W., Falk, S.E., Houston, N.A., Peterson, S.M., Westenbroek, S.M., and Christenson, S.C., 2011, Selected approaches to estimate water-budget components of the High Plains, 1940 through 1949 and 2000 through 2009: U.S. Geological Survey Scientific Investigations Report 2011–5183, 79 p.

Floridan Aquifer System

Bellino, J.C., 2011, Digital surfaces and hydrogeologic data for the Floridan aquifer system in Florida and in parts of Georgia, Alabama, and South Carolina: U.S. Geological Survey Data Series 584.

Kinnaman, S.L., 2011, Synoptic water-level measurements of the Upper Floridan aquifer in Florida and in parts of Georgia, South Carolina, and Alabama, May-June 2010: U.S. Geological Survey Data Series 639.

Kinnaman, S.L., Dixon, J.F., 2011, Potentiometric Surface of the Upper Floridan aquifer in Florida and in parts of Georgia, South Carolina, and Alabama, May 2010: U.S. Geological Survey Scientific Investigations Map 3182, 1 sheet.

Kuniansky, E.L., 2016, Simulating groundwater flow in karst aquifers with distributed parameter models—Comparison of porous-equivalent media and hybrid flow approaches: U.S. Geological Survey Scientific Investigations Report 2016–5116, 14 p., http://dx.doi.org/10.3133/sir20165116

Kuniansky, E.L. and Bellino, J.C., 2012, Tabulated Transmissivity and Storage Properties of the Floridan Aquifer System in Florida and parts of Georgia, South Carolina, and Alabama (ver. 1.1, May 2016): U.S. Geological Survey Data Series 669, 37 p.

Kuniansky, E.L., Bellino, J.C., and Dixon, J.F., 2012, Transmissivity of the upper Floridan aquifer in Florida and parts of Georgia, South Carolina, and Alabama: U.S. Geological Survey Scientific Investigations Map 3204, 1 sheet.

Williams, L.J., and Gill, H.E., 2010, Revised hydrogeologic framework of the Floridan aquifer system in the northern coastal area of Georgia and adjacent parts of South Carolina: U.S. Geological Survey Scientific Investigations Report 2010-5158, 103 p., 3 pls.

Williams, L.J., Raines, J.E., and Lanning, A.E., 2013, Geophysical Log Database for the Floridan Aquifer System and Southeastern Coastal Plain Aquifer System in Florida and Parts of Georgia, Alabama, and South Carolina: U.S. Geological Survey Data Series 760, 11 p.

Williams, L.J., and Kuniansky, E.L., 2015, Revised hydrogeologic framework of the Floridan aquifer system in Florida and parts of Georgia, Alabama, and South Carolina: U.S. Geological Survey Professional Paper 1807, 140 p., 23 pls., http://dx.doi.org/10.3133/pp1807.

Williams, L.J., and Dixon, J.F., 2015, Digital surfaces and thicknesses of selected hydrogeologic units of the Floridan aquifer system in Florida and parts of Georgia, Alabama, and South Carolina: U.S. Geological Survey Data Series 926, 24 p., http://dx.doi.org/10.3133/ds926.

Northern Atlantic Coastal Plain Aquifer System

Charles, E.G., 2016, Regional chloride distribution in the Northern Atlantic Coastal Plain aquifer system from Long Island, New York, to North Carolina: U.S. Geological Survey Scientific Investigations Report 2016 –5034, 
37 p. [Also available at http://dx.doi.org/10.3133/sir20165034.]

Eggleston, Jack, and Pope, Jason, 2013, Land subsidence and relative sea-level rise in the southern Chesapeake Bay region: U.S. Geological Survey Circular 1392, 30 p. [Also available at http://pubs.er.usgs.gov/publication/cir1392.]

Finkelstein, J.S., and Nardi, M.R., 2015, Geospatial compilation and digital map of center pivot irrigated areas in the mid-Atlantic region, United States: U.S. Geological Survey Data Series 932, accessed May 25, 2016, at http://pubs.er.usgs.gov/publication/ds932.

Masterson, J.P., Pope, J.P., Fienen, M.N., Monti, Jack, Jr., Nardi, M.R., and Finkelstein, J.S., 2016a, Assessment of groundwater availability in the Northern Atlantic Coastal Plain aquifer system from Long Island, New York, to North Carolina: U.S. Geological Survey Professional Paper 1829, 76 p. [Also available at http://dx.doi.org/10.3133/pp1829.]

Masterson, J.P., Pope, J.P., Fienen, M.N., Monti, Jack, Jr., Nardi, M.R., and Finkelstein, J.S., 2016b, Documentation of a groundwater flow model developed to assess groundwater availability in the Northern Atlantic Coastal Plain aquifer system from Long Island, New York, to North Carolina: U.S. Geological Survey Scientific Investigations Report 2016–5076, 70 p. [Also available at http://dx.doi.org/10.3133/sir20165076.]

Masterson, J.P., Pope, J.P., 2016, Sustainability of groundwater supplies in the Northern Atlantic Coastal Plain aquifer system:  U.S. Geological Survey Fact Sheet 2016-3046, 6p. [Also available at http://dx.doi.org/10.3133/fs20163046.]

Masterson, J.P., Pope, J.P., Monti, Jack, Jr., Nardi, M.R., Finkelstein, J.S., and McCoy, K.J., 2013b, Hydrogeology and hydrologic conditions of the Northern Atlantic Coastal Plain aquifer system from Long Island, New York, to North Carolina: U.S. Geological Survey Scientific Investigations Report 2013–5133, 76 p. [Also available at http://dx.doi.org/10.3133/sir20135133.]

Masterson, J.P., Pope, J.P., Fienen, M.N., Monti, Jack, Jr., Nardi, M.R., and Finkelstein, J.S., 2011, assessing groundwater availability in the Northern Atlantic Coastal Plain aquifer system:  U.S. Geological Survey Fact Sheet 2011-3019 , accessed August 18, 2016, at http://pubs.usgs.gov/fs/2011/3019/

Pope, J.P., Andreasen, D.C., McFarland, E.R., and Watt, M.K., 2016, Digital elevations and extents of regional hydrogeologic units in the Northern Atlantic Coastal Plain aquifer system from Long Island, New York, to North Carolina:U.S. Geological Survey Data Series 996, 28 p., [ Also available at http://dx.doi.org/10.3133/ds996.]

Glacial Aquifer System

Callegary, J.B., Kikuchi, C.P., Koch, J.C., Lilly, M.R., Leake, S.L., 2013, Review: Groundwater in Alaska: Hydrogeology Journal, Vol. 21, Issue 1, pp 25-39. Invited submission to special issue on cold-region hydrology.

Bayless, E.R., Arihood, L.D., Reeves, H.W., Sperl, B.J, Stipe, V.E., and Bunch, A.R., 2017, Maps and grids of hydrogeologic information created from standardized water-well drillers’ records of the glaciated United States: U.S. Geological Survey Scientific Investigations Report 2015–5105, 34 p., https://doi.org/10.3133/sir20155105..

Fienen, M.F., and Plant, Nathaniel, 2014, A cross-validation package driving Netica with Python:  Environmental Modelling & Software, v. 63, p. 14-23, doi:10.1016/j.envsoft.2014.09.007

Fienen, M.N., Nolan, B.T., Feinstein, D.F., and Starn, J.J., 2015, Metamodels to bridge the gap between modeling and decision support: Groundwater, v. 53, no. 4, pg. 511-12, DOI: 10.1111/gwat.12339

Fienen, M.N., Nolan, B.T., and Feinstein, D.T., 2016, Evaluating the sources of water to wells— three methods for metamodeling of a groundwater flow model: Environmental Modelling & Software, v. 77, pg. 95-107, doi:10.1016/j.envsoft.2015.11.023

Feinstein, D., Fienen, M., Reeves, H., and Langevin, C., 2015, A semi-structured MODFLOW-USG model to evaluate local water sources to wells for decision support: Groundwater, v. 54, no. 4, pg. 532-544, DOI: 10.1111/gwat.12389

Kahle, S.C. and Futornick, Z.O., 2012, Bibliography of groundwater resources of the glacial aquifer systems in Washington, Idaho, and northwestern Montana, 1905-2011: U.S. Geological Survey Open-File Report 2012-1053, 32 p. http://pubs.usgs.gov/of/2012/1053/.

Williston and Powder River Aquifer System

Thamke, J.N., LeCain, G.D., Ryter, D.W., Sando, Roy, and Long, A.J., 2014, Hydrogeologic framework of the uppermost principal aquifer systems in the Williston and Powder River structural basins, United States and Canada: U.S. Geological Survey Scientific Investigations Report 2014–5047, 38 p., http://dx.doi.org/10.3133/sir20145047.

Long, A.J., Aurand, K.R., Bednar, J.M., Davis, K.W., Mckaskey, J.D.R.G., and Thamke, J.N., 2014, Conceptual model of the uppermost principal aquifer systems in the Williston and Powder River structural basins, United States and Canada: U.S. Geological Survey Scientific Investigations Report 2014–5055, 41 p., with appendix, http://dx.doi.org/10.3133/sir20145055.

Hawaii Volcanic-Rock Aquifer System

Izuka, S.K., Engott, J.A., Bassiouni, Maoya, Johnson, A.G., Miller, L.D., Rotzoll, Kolja, and Mair, Alan, 2016, Volcanic aquifers of Hawai‘i—hydrogeology, water budgets, and conceptual models: U.S. Geological Survey Scientific Investigations Report 2015-5164, 158 p., http://dx.doi.org/10.3133/sir20155164.

Engott, J.A., Johnson, A.G., Bassiouni, Maoya, and Izuka, S.K., 2015, Spatially distributed groundwater recharge for 2010 land cover estimated using a water-budget model for the Island of O‘ahu, Hawai‘i: U.S. Geological Survey Scientific Investigations Report 2015–5010, 49 p., http://dx.doi.org/10.3133/sir20155010.

Johnson, A.G., Engott, J.A., and Bassiouni, Maoya, 2014, Spatially distributed groundwater recharge estimated using a water-budget model for the Island of Maui, Hawai‘i, 1978–2007: U.S. Geological Survey Scientific Investigations Report 2014–5168, 53 p., http://dx.doi.org/10.3133/sir20145168.

Ozarks Plateaus Aquifer System

Knierim, K. J., Nottmeier, A. M., Worland, S., Westerman, D. A., and Clark, B. R., 2016, Groundwater withdrawal rates from the Ozark Plateaus aquifer system, 1900 to 2010, U.S. Geological Survey data release, https://dx.doi.org/10.5066/F7GQ6VV1.

Turner, N.L., Knierim, K.J., Kresse, T., 2016, Sinkholes and Springs of the Ozark Physiographic Province, northern Arkansas, from Topographic Maps: U.S. Geological Survey data release, http://dx.doi.org/10.5066/F7XK8CNZ.

Nottmeier, A.M., 2016, Regional potentiometric surface dataset of the Ozark aquifer in Arkansas, Kansas, Missouri, and Oklahoma, November 2014 - January 2015: U.S. Geological Survey data release, http://dx.doi.org/10.5066/F74747XS.

Nottmeier, A.M., 2015, Regional potentiometric surface of the Ozark aquifer in Arkansas, Kansas, Missouri, and Oklahoma, November 2014–January 2015: U.S. Geological Survey Scientific Investigations Map 3348, 1 sheet,http://dx.doi.org/10.3133/sim3348.

Knierim, K.J., Wagner, D.M., Roland, V.L., and Nottmeier, A.M., 2015, Ozark Plateaus seepage run dataset, southern Missouri and northern Arkansas, 1982-2006: U.S. Geological Survey data release, http://dx.doi.org/10.5066/F7W9577Q.

Clark, B.R., 2015, Groundwater, a source to streams in the Ozark Plateaus: video, accessed at https://www.youtube.com/watch?v=CTw4cfZyTMw

Pennsylvanian and Mississippian Aquifer System of the Appalachian Plateaus

Ladd, D.E., 2016, Mean-annual and mean-seasonal water-budget estimates from a Soil-Water-Balance model of the Appalachian Plateaus, 1980 through 2011, U.S. Geological Survey Data Release, http://dx.doi.org/10.5066/F7X06544

McCoy, K.J., Yager, R.M., Nelms, D.L., Ladd, D.E., Monti, Jack, Jr., and Kozar, M.D., 2015, Hydrologic budget and conditions of Permian, Pennsylvanian, and Mississippian aquifers in the Appalachian Plateaus Physiographic Province (ver. 1.1, October 2015): U.S. Geological Survey Scientific Investigations Report 2015–5106, 77 p., http://dx.doi.org/10.3133/sir20155106.

Nelms, D.L., Messinger, Terence, and McCoy, K.J., 2015, Annual and average estimates of water-budget components based on hydrograph separation and PRISM precipitation for gaged basins in the Appalachian Plateaus Region, 1900–2011: U.S. Geological Survey Data Series 944, 10 p., http://dx.doi.org/10.3133/ds944.

Transboundary Aquifer Assessment Program

The United States-Mexico Transboundary Aquifer Assessment Program (TAAP) was congressionally authorized under Public Law 109-448 in 2006 for 10 years to conduct binational scientific research to assess certain priority transboundary aquifers: the San Pedro, Santa Cruz, Mesilla-Conejos Medanos, and Hueco Bolson aquifers. Of the $50M authorized under the legislation, $2M was appropriated from 2008-10, and $1M in 2016. Funding was divided equally among the Water Science Centers and Water Resources Research Institutes of Arizona, New Mexico, and Texas. Additional funding sources supported the program in years without appropriations. The program has come under the auspices of the Water Availability and Use Science Program and is listed as one of the regional groundwater availability studies.

Browning-Aiken, Anne, Scott, C.A., Varady, R.G., and Megdal, S.B., 2010, Spanning transboundary waters in North America (Atravesando las aguas transfronterizas en América del Norte, Traverser les eaux transfrontières en Amérique du Nord): Newsletter of International Network of Basin Organizations.

Callegary, J.B., Minjárez Sosa, I., Tapia Villaseñor, E.M., dos Santos, P., Monreal Saavedra, R., Grijalva Noriega, F.J., Huth, A.K., Gray, F., Scott, C.A., Megdal, S.B., Oroz Ramos, L.A., Rangel Medina, M., Leenhouts, J.M., 2016, San Pedro River Aquifer Binational Report: International Boundary and Water Commission, 170 p.

Callegary, J.B.; Langeman, Jeff; Leenhouts, James; Martin, Peter; 2013, Challenge theme 2: assuring water availability and quality in the 21st century: Chapter 4 in United States--Mexican Borderlands--facing tomorrow’s challenges through USGS science, eds. Randall Updike, Eugene Ellis, William Page, Melanie Parker, Jay Hestbeck, William Horak, USGS Circular 1380-4

Culbertson, Chris, Lytle, W.E., McMillan, M.M., Sternberg, B.K., and Withers, K.B., 2010, Transient electromagnetic (TEM) investigation of microbasin morphology along the Santa Cruz River, Nogales,

Arizona: University of Arizona, Geophysical Field Methods Spring, 2010 Course Report, accessed June 19, 2012, at http://www.lasi.arizona.edu/GEN%20416-516%202010%20Final%20Report.pdf.

Gungle, Bruce, Callegary, J.B., Paretti, N.V., Kennedy, J.R., Eastoe, C.J., Turner, D.S., Dickinson, J.E., Levick, L.R., and Sugg, Z.P., 2016, Hydrological conditions and evaluation of sustainable groundwater use in the Sierra Vista Subwatershed, Upper San Pedro Basin, southeastern Arizona: U.S. Geological Survey Scientific Investigations Report 2016–5114, 90 p., http://dx.doi.org/10.3133/sir20165114.

Kambhammettu, B.V.N.P., Chandramouli, S., and King, J.P., 2011, An improved DEM aggregation technique for models with non-uniform resolution: International Journal of Geomatics and Geosciences, v. 1, no. 4, p. 962–970.

Kambhammettu, B.V.N.P., King, J.P., and Allena, Praveena, 2011, Evaluation of mountain-front recharge estimation techniques for Southern New Mexico basins: International Journal of Water Resources and Environmental Engineering, v. 3, no. 3, p. 66–72.

Kambhammettu, B.V.N.P., Schmid, Wolfgang, King, J.P., and Creel, B.J., 2012, Effect of elevation resolution on evapotranspiration simulations using MODFLOW: Ground Water, v. 50, no. 3,  p. 367–375.

Lincicome, A.D., 2011, DRASTIC groundwater vulnerability assessment of the Santa Cruz and San Pedro aquifers: The University of Arizona, Soil, Water, and Environmental Sciences, Master’s Thesis.

Maddock, Thomas, III, Baird, K.J., Hanson, R.T., Schmid, Wolfgang, and Ajami, Hoori, 2012, RIP-ET: A riparian evapotranspiration package for MODFLOW-2005: U.S. Geological Survey Techniques and Methods 6–A39, 76 p.

McAndrew, R.M., 2011, Subsurface contaminant transport modeling in the upper Santa Cruz Basin: The University of Arizona, Hydrology and Water Resources, Master’s Thesis.

Megdal, Sharon, Varady, Robert, Vandervoet, Prescott, and Scott, Chris, 2012, Water allocation under uncertainty: Groundwater and effluent in the United States – Mexico transboundary Santa Cruz River Basin: The Third United Nations World Water Development Report (WWDR4) Case Studies Volume, UNESCO.

Megdal, S.B., 2008, Front-row view of federal water lawmaking shows process works – U.S. Mexico Transboundary Aquifer Assessment Act pondered, passed and signed, in Norman, L.M., Hirsch, D.D., and Ward, A.W., eds., Proceedings of a USGS Workshop on facing tomorrow's challenges along the U.S. – Mexico border: Monitoring, modeling, and forecasting change within the Arizona-Sonora transboundary watersheds: U.S Geological Survey Circular 1322.

Milman, A., and Scott, C.A., 2010, Beneath the surface: Intranational institutions and management of the United States – Mexico transboundary Santa Cruz aquifer: Environment and Planning C: Government and Policy, v. 28, p. 528–551.

Scott, C.A., 2011, The water-energy-climate nexus: Resources and policy outlook for aquifers in Mexico: Water Resources Research, v. 47, doi:10.1029/2011WR010805.

Scott, C.A., Megdal, Sharon, Oroz, L.A., Callegary, James, and Vandervoet, Prescott, 2012, Effects of climate change and population growth on the transboundary Santa Cruz aquifer: Climate Research,  v. 51, p. 159–170, doi: 10.3354/cr01061.

Scott, C.A., and Pasqualetti, M.J., 2010, Energy and water resources scarcity: Critical infrastructure for growth and economic development in Arizona and Sonora: Natural Resources Journal, v. 50, no. 3,  p. 645–682.

Scott, C.A., and Pineda-Pablos, N., 2011, Innovating resource regimes: Water, wastewater, and the institutional dynamics of urban hydraulic reach in northwest Mexico: Geoforum, v. 42, no. 4,  p. 439–450, doi:10.1016/j.geoforum.2011.02.003.

Stewart, A.M., Callegary, J.B., Smith, C.F., Gupta, H.V., Leenhouts, J.M., and Fritzinger, R.A., Use of the continuous slope-area method to estimate runoff in a network of ephemeral channels, southeast Arizona, U.S.A.: Journal of Hydrology, v. 472–473, p. 148–158.

Texas Water Resources Institute and New Mexico Water Resources Research Institute, 2008,  U.S.-Mexico Transboundary Aquifer Assessment Program- Arizona (TAAP-A/S): Fact Sheet.

Texas Water Resources Institute and New Mexico Water Resources Research Institute, 2009,  U.S.-Mexico Transboundary Aquifer Assessment Program- Arizona (TAAP-A/S): Fact Sheet.

Texas Water Resources Institute and New Mexico Water Resources Research Institute, 2010,  U.S.-Mexico Transboundary Aquifer Assessment Program- Arizona (TAAP-A/S): Fact Sheet.

Texas Water Resources Institute and New Mexico Water Resources Research Institute, 2011,  U.S.-Mexico Transboundary Aquifer Assessment Program- Arizona (TAAP-A/S): Fact Sheet.

Wilder, M., Scott, C.A., Pineda-Pablos, N., Varady, R.G., Garfin, G.M., and McEvoy, J., 2010, Adapting across boundaries: Climate change, social learning, and resilience in the U.S. – Mexico border region: Annals of the Association of American Geographers, v. 100, no. 4, p. 917–928.